## Slide 1: MANAGE AND IMPLEMENT SMALL PROJECTS
D1.HGE.CL7.04
D1.HGA.CL6.11
Notes: Trainer welcomes trainees to class.

## Slide 2: Manage and implement small projects
This Unit comprises three Elements:
Plan project
1
Administer and monitor project
2
Evaluate project
3
Notes: Trainer advises trainees this Unit comprises three Elements, as listed on the slide explaining:
• Each Element comprises a number of Performance Criteria which will be identified throughout the class and explained in detail
• Trainees can obtain more detail from their Trainee Manual
• At times the course presents advice and information about various protocols but where their workplace requirements differ to what is presented, the workplace practices and standards, as well as policies and procedures must be observed

## Slide 3: Assessment
Assessment for this unit may include:
Oral questions
Written questions
Work projects
Workplace observation of practical skills
Practical exercises
Formal report from employer/supervisor
Notes: Trainer advises trainees that assessment for this Unit may take several forms, all of which are aimed at verifying they have achieved competency for the Unit as required.
Trainer indicates to trainees the methods of assessment that will be applied to them for this Unit.

## Slide 4: Plan project
Performance Criteria for this Element are:
Develop the objectives and scope of the project in consultation with appropriate colleagues and customers
Determine and develop a resource strategy for the project
Evaluate the financial viability of the project through analysis of key factors
Plan and create an administrative structure for the project
Allocate project responsibilities in agreement with others, and clearly communicate responsibilities to all involved
Plan internal and external communications and public relations and marketing strategies together with appropriate colleagues
Notes:   Trainer identifies for trainees the Performance Criteria for this Element, as listed on the slide.

## Slide 5: Plan project
Reach agreement on suitable project evaluation methods
Develop an overall project management plan and communicate plan to appropriate colleagues
Identify key project milestones and communicate these to persons involved
Notes:   Trainer identifies for trainees the Performance Criteria for this Element, as listed on the slide.
Class Activity – General Discussion
Trainer leads a general class discussion on planning projects by asking questions such as:
What small projects might a venue undertake?
Why are small projects important to the operation of a business?
What do you think is involved in planning a small project?
Who from outside the venue might be involved in planning activities for a small project?
Who from inside the venue might be involved in planning activities for a small project?
What plans and strategies are used as part of the planning process for a small project?

## Slide 6: Develop objectives and scope
Project management involves:
Planning and preparation
Organising and arranging
Resource identification and administration
Monitoring
Project evaluation
Notes: Trainer explains that, while there are no strict definitions for the terms ‘project management’, it can be seen as a series of activities undertaken by a person (or group of people) to achieve the defined/stated objectives of a project while making sure the limitations/constraints that apply to the project are observed.
The central activities involved in project management can be seen as:
Planning and preparation
Organising and arranging
Resource identification and acquisition
Project implementation and administration
Monitoring activities – before and during the project
Project evaluation – review and assessment.

## Slide 7: Develop objectives and scope
Characteristics of a project:
They are temporary in nature
They have a beginning and an end
They have stated goals and objectives
They have limitations and constraints
They require collaboration with others
Notes: Trainer defines characteristics of a project:
They are temporary/transient in nature – they do not exist as part of the everyday, ongoing activities/business of the organisation
They have a beginning – there is a start date
They have an end date – there is a final date for completion
They have stated goals/objectives – these outline/specify what the project is expected to achieve: they may be called ‘project deliverables’
They have limitations, restrictions, constraints – all projects must (for example) fit within a budget, occur within a specified physical area, only involve nominated people and/or resources
They require interaction and collaboration with others to determine and approve decisions to be made and action to be taken, to obtain relevant information and to assist in numerous ways with project management activities.

## Slide 8: Develop objectives and scope
‘Small’ projects are limited by one or more of:
Duration
Resources required – physical, human, financial
Information required
Complexity
Notes: Trainer explains ‘small’ projects are limited by one or more of the following factors:
Duration – the length of time the project will take from ’start’ to ‘finish’ is comparatively short. Timeframes for small projects exists traditionally within the ‘one week’ to ‘three months’ range.
Physical resources involved – small projects generally require significantly fewer physical resources than is the case for major projects
Human resources required – a small project can sometimes involve only you in conjunction with designated external stakeholders. Sometimes the small project may require you to be assisted by a limited number of internal staff, or the involvement of workplace staff for a nominated number of hours.
Financial resources committed – generally speaking a small project generally involves less money
Information necessary – compared to large/major project a small project often requires very little information from within the organisation and from outside the organisation (from external customers, suppliers, businesses, agencies or authorities)
Complexity – small projects are usually quite simple and straightforward.

## Slide 9: Develop objectives and scope
When managing a small project:
You will have to do ‘normal’ duties at the same time
Major projects have a dedicated PM
You need to be skilled at:
Time management
Delegating
Multi-tasking
Notes: Trainer states:
When managing a small project you will often be expected to also undertake your ‘normal’ workplace duties and while managing the small project
Large/major projects often have a Project Manager whereas small projects do not
This means you will need to become quickly skilled at:
  Time management – to ensure all your traditional work is completed as required, plus ensure all the requirements of the project are fulfilled
  Delegating – most supervisors/managers who are handed project management responsibilities will need to share their normal workload by delegating it to others
  Multi-tasking – developing the ability and capacity to do numerous things at the same time.

## Slide 10: Develop objectives and scope
Examples of small projects:
Conferences and meetings, promotional events and functions
Introduction of new technology and systems into the workplace
Product development
Research
Ongoing business projects
Notes: Trainer gives examples of small projects:
Conferences and meetings, promotional events and functions conducted on-site or at a remote venue for a client as a component of the MICE industry sector.
Introduction of new technology or systems into the workplace to increase efficiency, save money, meet marketplace competition, comply with a legislated obligation and/or satisfy identified customer demand
Product development which can be seen as relating to:
  The creation of a new product or the development of an upgraded product based on an existing product
  The development of packages
  Service enhancement including the development of service quality criteria
  Refurbishing
Research projects for a range of topics which may include:
  Customer satisfaction surveys
  Resource acquisition
  Legislated compliance requirements
Ongoing business projects such as taking responsibility for delivering one component of a bigger ‘major’ project, for example:
  You might have responsibility for the food and beverage elements of a function but not responsibility for staffing, security, entertainment or other aspects of the event
  You may be asked to handle the purchase of tables and chairs for a refurbished restaurant but not be involved in the planning and building stages, the decoration or the development of new menus
  You may be asked to undertake specified market research activities if the venue has embarked on a wider project to attract a new target market.
Class Activity – Discussion
Trainer asks students to identify and describe a range of small industry-related project identifying what is involved in each.

## Slide 11: Develop objectives and scope
May be a need to consult with:
Other supervisors
Owners and/or managers
Staff
The client
Attendees
Government authorities and agencies
Notes: Trainer highlights that there is commonly a need when managing a small project to cooperate, collaborate and consult with others in relation to the project explaining there may need to consult with:
Other supervisors from other departments or sections
Managers of other divisions or areas
Owners of the business
Staff from relevant operational departments
The client where there is a person/organisation paying for an event/function
Attendees at an event/function to determine their needs, wants and preferences
Providers and suppliers – these are the businesses who sell you the goods and services needed to undertake/support the implementation of a project
Government authorities and agencies to determine legal compliance requirements, and to solicit support and assistance with implementation of the project.
The requirement to consult with others frequently/usually extends beyond the vital planning phase into the implementation stages of the project.

## Slide 12: Develop objectives and scope
Ways to engage with staff who are involved with project work include:
Develop project teams
Discuss issues at staff meetings and briefings
Hold special meetings just for the project
(Continued)
Notes: Trainer states the following have proved effective in engaging with staff in project work:
Develop dedicated project teams
Discuss the project at staff meetings, team briefings and similar
Hold a special staff meeting (or series of meetings) with a sole focus on the project

## Slide 13: Develop objectives and scope
Involve staff with previous project experience
Invite staff to participate
Pay staff to participate
Thank people
Recognise and acknowledge contributions
Notes: Trainer continues explaining ways to engage with staff in project work:
Involve staff who participated in other/similar projects either at the venue or at other businesses where they have worked
Ask/invite staff to participate – never assume staff will participate or will want to participate
Pay staff to participate – consult and meet during work hours as opposed to expecting staff to participate in their own time
Thank people for participating and contributing
Recognise and acknowledge contributions made.

## Slide 14: Develop objectives and scope
‘Project scope’:
Sets out scope of the project
Identifies tasks and deliverables for the project
Spells out your responsibility for the project
The budget for the project is based on this
Notes: Trainer introduces ‘project scope’ stating:
A project scope statement sets out the scope of the project.
This scope refers to identifying the things (tasks, project deliverables) that have to be completed for the project to be successfully completed.
It therefore defines your responsibility for the project. If matters are not covered by the project scope (statement) then they are, quite simply, not part of the project and not your responsibility.
Great attention is paid to producing this document as it provides the basis for determining the budget required to enable the project to proceed/succeed.

## Slide 15: Develop objectives and scope
Contents of ‘Project scope statement’:
Justification or rationale for the project
Deliverables
Name of client or delegating or funding body
(Continued)
Notes: Trainer explains there is no standard format for Scope Statements but they can be expected to cover/address:
Justification/rationale for the project – explaining why the project is taking place which may take into account market research findings, internal demand for whatever is the focus of the project, for example:
  Need for increased dining areas
  Need for more room for front office
  Need for extra external entertainment facilities
  Need for room renovations
  Need to respond to taken by competition/other venues which threaten the ongoing viability of the business
  Need to comply with a legal obligation
Project deliverables – there can be two types of ‘deliverables.
  One type relates to milestones to be achieved/delivered within the duration of the project. These are similar to KPIs designed to help determine if the project is on track or not by set dates.
  The second type of deliverable is the end product/s for the project. These are the ‘things’ the project is intended to achieve when it is complete
Name of the client or delegating or funding body. This will often be the business itself because most small projects are initiated by the business on its own behalf/for its own benefit.
  Where the project is commissioned by a customer, or an outside agency or client their name and contact details will be provided and they are identified as the client/delegating body.

## Slide 16: Develop objectives and scope
SMART Objectives:
Quantifiable outcomes
Budget
Quality indicators
Risks
Project management details
Notes: Trainer continues giving information about contents of project scope statement:
Objectives for the project. All projects have numerous objectives and this section will set out:
  All quantifiable outcomes the project is intended to achieve
  The budget available
  Relevant quality indicators specifying the intended level of quality to be achieved by activities and outcomes.
  A standard requirement is all objectives for the project must conform to the SMART acronym meaning they must all be:
    Specific, Measurable, Achievable, Realistic, Time-related and Trackable.
Risks identified for the project together with the level of acceptability and how to manage them
Project management details specifying who will have responsibility/responsibilities, and/or the structure of the project management team (which is often you, members of the Board and co-opted people as required/deemed appropriate).
Class Activity – Handout
Trainer distributes examples of Project scope statement and discusses same with students.

## Slide 17: Develop objectives and scope
Other project documentation you may need to read may include:
Contracts already entered into by the venue
Other agreements
Project brief
Project management plan
Notes: Trainer indicates PM may also need to access and read other documents relating to the project they are managing:
Contracts already entered into by the venue. These could be ongoing, pre-existing contracts (for maintenance, service, repairs, support, technology), or they could be contracts developed specifically for the project and entered into just for the project by senior management/owners.
Other agreements. It is also possible ‘other arrangements’ have been entered into by the business regarding the provision of services, joint venture arrangements, preferred supplier arrangements, MOUs or similar. You will be expected to function within the constraints these documents may impose
Project brief. This is a document similar to a Project Scope Statement that may identify ancillary project matters such as:
  Constraints, limitations and restrictions on the project
  Assumptions underpinning the rationale for the project
  The context for the project
  Stakeholders in the project
  A communication strategy for the project
  Relevant workplace policies
  Legislated requirements
  Project management plan. You may be required to prepare the Project Plan or you may be given one already prepared
  A range of supplementary documents tied to the specific nature of the project which, if not already contained in the above documents may address:
  Expected outcomes
  Inclusions and exclusions for the project
  Timeframes for the project and identified stages
  Quality standards/criteria for project deliverables
  Project resources.
Class Activity – Handouts
Trainer distributes and discusses documents as identified on the slide.

## Slide 18: Develop objectives and scope
Ensure you seek clarification about the project from (as applicable):
Delegating authority
Funding body
Management
Notes: Trainer emphasises need to seek clarification regarding project:
No project should proceed until there is total clarity about what the requirements of the project are.
A Project Manager can never assume they know what is required. All proposed action must be clarified, and there is sometimes a requirement all action must receive actual verbal or written approval before it can be taken..
The ‘delegating authority’ will depend on what the project is:
For functions/events the delegating authority could be an individual – a private person, or someone who represents a business.
Where finance for a building, renovation or upgrading project has been received from a funding body (such as an industry body, or a government authority), this body/agency becomes the delegating authority
In hospitality venues the Board, management or the owner is the delegating body for 99.9% of all projects (with the exception of, for example, functions).
In many ways, exactly who can be seen as the delegating authority depends on who is paying for things. The person/agency who pays is essentially the delegating authority.

## Slide 19: Develop objectives and scope
Clarify project parameters in regard to:
Clarify ambiguity
Resolve uncertainty
Determine sequencing and priorities
Determine inclusions
Discuss resources
(Continued)
Notes: Trainer stresses need to clarify project parameters with management, delegating authorities or funding bodies on topics such as:
Clarify ambiguity in any of the documents referred to above
Resolve uncertainty about standards/quality requirements for deliverables
Determine sequencing of competing action and priorities
Decide what is, and what is not, included in the project scope
Discuss and justify the need for extra resources

## Slide 20: Develop objectives and scope
Integration of this project with others
Research undertaken
Procurement protocols
Reporting requirements
Risk analysis
Notes: Trainer continues discussing need for clarification as part of the planning process:
Provide insight or direction regarding the integration of this project with other projects being undertaken by the business either previously, at the same time, or being planned/consider into the future
Research and/or give advice regarding legislative and quality standards especially relating to compliance, safety, protection of the organisation against legal action (civil as well as criminal)
Clarify actions related to the procurement of items necessary for project implementation
Clarify the project reporting requirements. These are commonly spelled out in the project brief but can be subject to change over the duration of the project especially where the project exists over an extended period.
Give input regarding risk analysis regarding the project. This can necessitate their involvement in:
  Evaluating and classifying new risks emerging as the project unfolds undertaking formal risk analysis
  Revising and/or verifying likelihood and consequences
  Deciding on the risk management strategy for identified risks
  It must be standard practice for all projects to include consideration of safety (as it impacts on customers, staff, sub-contractors, members of the public, suppliers) as part of its risk analysis and management.

## Slide 21: Develop objectives and scope
Determine your personal limits. These may be:
Normal ‘scope of responsibility’
Extra authority as appropriate:
To access data
To spend money
To attend meetings
To give directions
Never assume you have authority.
Notes: Trainer stresses need for students to identify their personal limits in relation to the project they are managing stating they will usually have their normal authority plus extra scope of authority which may mean they are:
Given access to statistics, information and other internal business data you do not normally have
Granted authority to spend money on the project on behalf of the organisation in areas you do not normally spend money in, or to a greater extent than you are normally entitled/allowed to do
Required to attend certain meetings, for example, with management, the client, delegating authorities, other departments
Authorised to give directions and instructions to staff who are not normally your sub-ordinates.
Never assume authority goes with responsibility
It is vital you determine exactly what you are authorised to do when given project management responsibilities.
Never believe you are automatically given everything and anything you need to get the job done.
In fact, in some cases (relatively few) you may be given no extra authority despite being substantial additional responsibility.
Where you believe the authority you have been given does not match the need for authority you need, you must meet with management or the delegating authority to negotiate extra/necessary authority.
One of the biggest impediments to an individual successfully managing a project is to be hamstrung, not by cash or resources, but by the inability to make decisions and take action as you believe they are warranted by the project.

## Slide 22: Develop objectives and scope
Reporting requirements for project:
Attention to detail
Truth and honesty
Timely production of reports
Reference to evidence
Comparison of actual achievements against projections
(Continued)
Notes: Trainer presents information relating to project reporting requirements identifying report characteristics:
Attention to detail
Truth and honesty – full disclosure is vital
Producing documentation (that is, a formal Report, an Interim report, and a Final report) to be distributed to those authorised to receive it, and filed for future reference
Evidence of claims and statements such as copies of quotations and invoices, photographs, claims for payment, receipts for money spent
Comparison of actual progress against KPIs, milestones and stages for the project

## Slide 23: Develop objectives and scope
Issues arising
Need for extra resources
Timing issues
Q and A session
Only provided to those on the approved ‘Distribution List’
Notes: Trainer continues to present information relating to project reporting requirements identifying report characteristics:
Issues arising mentioning:
  Unexpected expenses
  Unforeseen problems and issues and how they are being addressed
Requests relating to need for extra resources
Identification of instances where the project is expected to finish before expected completion date and/or where it appears the project will experience a time over-run or cannot be finished at all
Question and Answer session to allow others to question action taken, problems encountered, quality and/or quantity of deliverables
Need to release/forward reports only to those listed on a Distribution List for the project.

## Slide 24: Develop objectives and scope
Reporting frequency may be:
Daily
Nominated meetings
‘As required’
On given dates
For the Annual Report
Notes: Trainer discusses possible frequency of project reporting requirements:
On a daily basis to the Manager as part of the daily management meetings held amongst the venue management team
At every Board or management meeting. This usually means once a month
At every committee/sub-committee meeting convened to assist with the project. This requirement is in addition to the need to report to the Board/management
When required by stakeholders and/or delegating authorities (with the approval of venue management)
At nominated dates as indicated by the formalised ‘reporting requirements’ contained in the project brief or communications plan for the project
For the Annual Report prepared for the organisation.

## Slide 25: Develop objectives and scope
Tips for success in project management:
Be prepared to ask for help
Identify assistance available
Think before you act
Seek approval before you take action if possible
Allocate specific time for project work
Notes: Trainer presents tips for success in project management:
Never be afraid of asking for help from the Manager, the owner or other managers/supervisors
Identify the assistance available within the venue. This means making enquiries about the experience and expertise of Board members, supervisors, staff and those in your network of industry contacts: these people can be valuable resources
Think before you act – planning and preparation are vital for all projects. Supervisors/managers in the hospitality industry are used to making quick decisions in normal everyday working situations but projects are different given their importance, the money involved and their potential impact so it is important to understand the same ‘quick response’ strategy is not to be applied when managing a project
Wherever possible seek approval for action before taking the action. This is not always possible, but it is always a good idea to present your proposed course of action to management or a designated sub-committee (established just for the project) or Manager and obtain their approval to proceed
Try to block out certain times on certain days to do nothing but project work. If you are able to do this it means you have a given amount of time free from other interruptions/calls on your time to spend solely on the project. This is a good thing to do because project management demands concentration, time, and focus.
Class Activity – Guest Speaker
Trainer arranges for a relevant PM to attend and:
Discuss their role
Explain the work they do
Give examples of projects they have
Provide advice to students.

## Slide 26: Determine and develop resource strategy
A resource strategy identifies:
How to obtain required resources
Develop resources
Maintain resources
Use and manage resources
May be in ‘written’ form or in ‘mental’ form only.
Notes: Trainer states all projects require students to acquire and apply certain resources explaining a resource strategy is a plan on how they intend achieving one or more of the following (depending on the project, and the type of resource being considered):
Obtaining the necessary resources required to undertake the project you are managing
Developing the resources to ensure they allow you to achieve the objectives of the project and comply with applicable requirements and/or constraints
Maintaining the resources so they remain effective and efficient and their useful life is extended
Using and managing resources for optimal outcomes.
The resource strategy (also known as a ‘resources strategy’) for a small project may:
Be prepared in written form as a formal or semi-formal plan
Exist only in your mind as a result of mentally considering the resources required and how you may acquire them.

## Slide 27: Determine and develop resource strategy
Resources include:
Human resources
Physical resources
Financial resources
Information
Notes: Trainer states specific resources required for each small project will obviously vary depending on the type and scope of the project and the objectives which have to be achieved but will always comprise a combination of:
Human resources
Physical resources
Financial resources
Information.

## Slide 28: Determine and develop resource strategy
HR strategy relates to staffing for the project and will address:
Full-time, part-time and casual mix
Use of external contractors
Experience and expertise required
Hours
Notes: Trainer discusses Human resources strategy as this relates to the staff/personnel required for a project stating consideration may be given to:
The use or blend of permanent, part-time and casual employees
Including external providers or suppliers such as contractors
The experience and expertise the individuals or organisations need to have in relation to the project
Hours to be worked and paid for from the project budget/s

## Slide 29: Determine and develop resource strategy
Physical resources strategy relates to machinery, equipment, materials and assets required to:
Plan and prepare for the project
Implement the project
Support the work of those involved in the project
Notes: Trainer discusses Physical resources strategy for a project which relates to machinery, equipment, utensil and other material assets required to:
Plan and prepare for the project such as tools of the trade, computers software and hardware to enable planning and project management
Implement the project such as the requirements identified as ‘deliverables’ in the project scope/brief
Support the work of others connected with planning and implementing the project.

## Slide 30: Determine and develop resource strategy
Financial resources strategy relates to funding for the project as applicable to:
Paying staff
Engaging external providers
Procurement
Notes: Trainer discusses financial resources strategy explaining this is the money available to enable payment for all project-related requirements which can include:
Paying staff
Engaging external consultants and contractors
Purchasing the physical assets/resources required

## Slide 31: Determine and develop resource strategy
Information strategy may address:
Internal policies and procedures
Dates and times
Numbers attending a function/event
Information known by management and other stakeholders
Notes: Trainer presents the Information strategy for a project identifying this is on often overlooked resource for projects but nonetheless an extremely critical element both for planning and project implementation and it relates to a variety of usuall ynon-negotiable factors impacting on the project such as:
Internal policies and procedures which must be accommodated
Dates, times and numbers/statistics relating to the project, for example:
  Days and date of a function
  Numbers attending a function or event
Knowledge held by management or other stakeholders which you need to know in order to properly plan and execute the project

## Slide 32: Determine and develop resource strategy
The HR strategy can also include:
Staff selection
Training
Role of external recruitment agencies
Re-allocating work
Backfilling
Notes: Trainer presents more information relating to the contents of the HR strategy:
Selecting internal staff to participate in the project
Providing relevant staff training as required
Using external staff recruitment agencies to source staff
Re-allocating work so required staff are free to engage with the project
Backfilling staff who are required to work on the project

## Slide 33: Determine and develop resource strategy
The physical resources strategy can also include:
Equipment and operating specifications
Supplier identification
Testing and trialling
Quotations and contracts
Comparison of options
(Continued)
Notes: Trainer presents more information relating to the contents of the physical resources strategy:
Determining specifications and operating requirements for each item to reflect project requirements
Identifying possible providers/suppliers
Trialling materials and services
Arranging for quotations and negotiating contracts
Comparing options for acquiring assets such as:
  Purchasing
  Leasing
  Rental

## Slide 34: Determine and develop resource strategy
Cost-benefit analysis
Acquisition options
Installation, commissioning and service/maintenance
Disposal of ‘old’ items
Notes: Trainer continues presenting more information relating to the contents of the physical resources strategy:
Undertaking a cost-benefit analysis for items which are significant in terms of their purchase price (see section 1.3 for more detail)
Considering alternative acquisition options such as:
  Borrowing items from other venues
  Asking other organisations in the chain for a loan of items
  Asking providers/suppliers to donate items
  Joint purchasing with other businesses
Arranging installation, commissioning and regular maintenance/servicing of equipment and systems including staff training as and if required relating to these new items
Identifying disposal arrangements for ‘old’ items being replaced as well as potential reselling/on-selling arrangements when new items have reached the end of their useful/effective life.

## Slide 35: Determine and develop resource strategy
The financial resources strategy can also include:
Formal project budget
Contributions and donations from others
Subsidies and grants
Optimal acquisition option for the business
Revenue generated from disposals
Notes: Trainer presents more information relating to the contents of the financial resources strategy:
Seeking a formal budget from management
Asking providers/suppliers for a contribution/donation
Seeking subsidies or grants from government agencies, industry bodies or joint venture partners
Insisting on a purchasing option which brings a saving or other benefit to the business such as:
  Trade, volume or early payment discounts
  Deferred payment/extended terms of trade
  Inclusion of a free item/service or ‘bonus’ into the deal
Allocation of monies from the sale of ‘old’ equipment to specific revenue lines or budget lines.

## Slide 36: Determine and develop resource strategy
The financial information strategy can also include:
Document review
Discussions with others
Scheduling project-related meetings
Confidentiality
Sharing and distribution of information
Notes: Trainer presents more information relating to the contents of the information resources strategy:
Identifying and reviewing existing documents
Speaking with others who have previous relevant experience
Scheduling meetings with stakeholders
Specifying actions to ensure information remains private and confidential
Requirements for sharing/distributing information to stakeholders.

## Slide 37: Evaluate financial viability
For ‘internal’ projects:
Management decides if the project is viable
No need to engage in financial viability analysis
Notes: Trainer introduces concept of financial viability regarding projects indicating there are two orientations depending whether the project is an ‘internal’ or ‘external’ one stating:
When you are required to undertake a project imposed by the organisation this is an internal project.
Where you are directed to manage such a project the following normally applies:
  Management have decided the project must be undertaken. It will not be up to you to determine whether or not it should go ahead
  There is no need to engage in a financial viability analysis of the project. Management will have already done this.

## Slide 38: Evaluate financial viability
For ‘external’ projects:
There is a need to:
Achieve the ‘required’ level percentage of profit
Factor in ‘other imperatives’ as they apply to each individual project
Notes: Trainer explains considerations where the project is an external project:
Achieve required profit as determined by the organisation, based on revenue/sales
‘Other imperatives’ which may vary on an individual project basis and such circumstances may occur when:
  The client is deemed to be a VIP customer and management wishes to demonstrate the value they hold the customer in
  There is a cash flow crisis – see below ‘Evaluating financial viability’
  The venue is experiencing very low occupancy and/or low levels of trade and they wish to stimulate activity to help underpin the viability of the entire organisation
  The project is an especially prestigious one and management wants to make sure it is conducted at the venue so the business obtains publicity, prestige and market positioning from conducting the event.

## Slide 39: Evaluate financial viability
Evaluating financial viability may require you to determine:
Availability of funding
Cost of borrowing funds
Internal cash flow situation
(Continued)
Notes: Trainer explains evaluating financial viability of the project may require determination of:
The availability of short and/or long-term funding for the project which can involve:
  Establishing whether the required amount of money is available or not
  Identifying sources of finance
The cost of borrowing funds to enable the project to be implemented which may require you to:
  Find out interest rates
  Calculate payments required
  Identify dates for repayments
Internal cash flow situation of the venue which will indicate whether or not management are desperate for cash/revenue

## Slide 40: Evaluate financial viability
Market feasibility
Financial risk
Results of cost-benefit analysis
Impact of the project on the business
Notes: Trainer continues explaining evaluating financial viability of the project may require determination of:
Market feasibility which asks you to decide whether or not the client/the project is suitable to your business in terms of matters such as the reputation of the client, and whether or not they align with the markets your organisation is catering to
Level of financial risk involved which asks you to calculate the possible loss to your organisation against a number of potential eventualities such as:
  Failure by the client to settle their account once the project/event has been finalized
  The event failing to attract the numbers and revenue anticipated
  Risks applicable to the project/function which may include adverse weather, other functions/events being operated by other venues at the same time and other risks identified by a formal risk management process (involving risk identification, risk analysis and risk control)
The results of relevant cost-benefit analyses – see below
The impact of the project on other aspects of the business which may include consideration of how the project/event will impact:
  Other customers/guests using the venue
  Service levels provided to others
  Occupancy levels and the resultant demand for staff
  The potential to optimize revenue and/or profit, for example, the project/event may increase revenue but not optimize profit if all the rooms are sold at a low discount rate necessary to ‘win the business’
  Need for maintenance, service and repairs to the venue
  Requirement for extra staff and/or extra hours for staff.

## Slide 41: Evaluate financial viability
There is a need to consider:
Availability and capacity of resources:
Human
Physical
Compliance
Sufficiency
Suitability
(Continued)
Notes: Trainer identifies key factors to consider when evaluating financial viability:
Availability and capacity of resources
Do you have sufficient human resources to undertake the project?
Is there a need to train staff to achieve the required outcomes for the project and, if so, what is involved in terms of time and money in doing this?
If you do not have the required physical resources, can they be obtained from elsewhere and if so, what is the cost?
Are the available physical resources suitable for the specific requirements of the project and are they serviced, safe and ready to use? If not, what is involved in making these existing resources fit to use?
Do the resources you have meet all legal compliance requirements?
Are the available resources sufficient in number to meet expected demand for the project?
Is the venue appropriate for conducting the required event/function? If not, what changes have to be made to ensure the venue is suitable?
Is there a need for the resources of the venue to integrate with resources being brought or used by those attending?

## Slide 42: Evaluate financial viability
Budget:
Amount
Availability
Authorities
Source
(Continued)
Notes: Trainer continues identifying key factors to consider when evaluating financial viability:
Budget
How much money is available?
When is it available?
How do you access it?
What authority do you need in order to spend it?
Can you obtain extra funding if needed?
Where will the extra funding come from?
Can you transfer money from one budget/budget line to another if needed?

## Slide 43: Evaluate financial viability
Contractual obligations and penalties:
Promises made
Potential for legal action
Financial penalties
Notes: Trainer continues identifying key factors to consider when evaluating financial viability:
Contractual obligations and penalties
What promises have been made to the client about resources and performance of the venue (in terms of products and service delivery)?
Which promises are legally-binding and/or non-negotiable?
Do the resources proposed and/or available align with promises made to the client regarding their performance, quality and other relevant factors?
What legal action might the client take for failure to meet performance standards/criteria in the contract which applies to the project/event?
What financial penalties (such as refunds and/or damages awarded if the venue is sued), and other penalties (such as a court injunction to re-perform the project/event or to issue a public apology) might flow if the agreed contract is not discharged in accordance wit all relevant terms and conditions?

## Slide 44: Evaluate financial viability
Cost-benefit analysis helps identify best purchasing option by considering:
Purchase price
Trade in
Benefits and savings which will flow
Ongoing cost of using the item
Opportunity cost
Expected life of the item
Impact on productivity
Notes: Trainer states a cost-benefit analysis is a common requirement in many organisations for all expenditure over a stated amount explaining:
Smaller, less expensive items or services are not usually subject to a cost-benefit analysis.
The cost-benefit analysis considers the costs and related benefits associated with making a nominated purchase and allows a mechanism whereby various alternatives can be compared against each other with a view to identifying the single most beneficial option for the business.
Factors considered as part of the cost-benefit analysis may include:
  Purchase price
  Trade-in or revenue obtained from selling ‘old’ item/s
  Benefits, savings and efficiencies gained
  Ongoing cost of service, repairs and maintenance
  Opportunity cost/s
  Expected life of the item
  Productivity.
Class Activity – Demonstration
Trainer demonstrates to students how to conduct a cost-benefit analysis for a nominated item.

## Slide 45: Evaluate financial viability
Project budget may be:
Set externally
Determined by the venue
Notes: Trainer presents basic information about project budgets stating:
The majority of projects are budget-based. There will normally be a limit on how much can be spent (or otherwise invested – such as time, effort, venue resources) to achieve the stated project deliverables.
The amount of money available for a project may have been:
  Set by the client funding body and/or the delegating authority, for example, the client may have a budget of 50,000 for their function, or the authority issuing the grant money may cap its funding to 75,000 for each project
  Determined by the venue – this is where management prescribes a maximum amount that can be spent on the project to achieve the outcomes identified in the Project Scope and/or Plans.

## Slide 46: Evaluate financial viability
When client sets budget, Project Manager (PM) role is to:
Deliver within these parameters
Meet and discuss project with client
Negotiate potential for extra payment
Obtain a written contract
Secure payment
Notes: Trainer presents information about situations where the client sets the budget for a project explaining PM role is to:
Deliver the goods and services as required within the budget limitations – attention needs to be paid to ensuring required (or expected, or ‘promised’) delivery/service standards while still returning the venue an acceptable level of profit/return. Note: some clients (especially valued, regular and VIP customers) have unrealistic expectations or make unreasonable demands on your venue they would not make on another venue. This may be because they feel/believe your property is obliged to provide them with more/a better deal given their value to the business.
Meet with the client and discuss their expectations, needs, wants and preferences. Avoid making promises which create unrealistic, unprofitable and/or unachievable deliverables in terms of timing, quantities, types of food and beverages to be provided, staff numbers, rooms/areas to be used, complimentary items to be provided
Negotiate extra payment. This is a core requirement for many projects: you have to be prepared to explain/justify why extra money is/may be needed to provide a project/function to meet client expectations. Rarely is there an open cheque book for functions but you must make sure the client knows there is the potential for them to be charged extra if they use extra or demand more.
Obtain agreement in written form (such as a function contract) detailing what is being provided. This is vital to avoid confusion and disappointment about what is to be supplied (menu, drinks, entertainment), and also serves as the legally-binding document compelling the client to pay
Obtain payment including, for example, an initial deposit in accordance with venue requirements, progress payments (where applicable) and final payment.

## Slide 47: Evaluate financial viability
When funding body sets budget, standard requirements include:
Venue to contribute or match money provided
Money to be spent be set date
Money can only be spent on specified items
Money may have to be spent with nominated supplier
Detailed monitoring, reporting and accounting
Return of unused funds
Notes: Trainer states where money is received from a government or industry body (such as in the form of a grant or subsidy) standard requirements are:
The venue may be required to match the grant money in some way. A ‘one for one’ requirement is common: you need to check this prior to accepting any grant to make sure management is prepared to commit the required funds
There are always requirements attached to the money. These are the ‘strings attached’ and can require you to:
  Spend money by a certain date
  Spend the money on a specified ‘thing’ or from items on a specified list of options
  Spend the money with a specified provider/supplier, for example, from a list of preferred suppliers/sponsors or with ‘local’ (or ‘domestic’) businesses
  Specified monitoring, reporting, record keeping and management requirements will apply
  Any unused money must be returned.
Class Activity – Guest Speaker
Trainer arranges for a representative from a government agency to attend and talk to students about requirements which attach to funding grants from this authority.

## Slide 48: Evaluate financial viability
Where the venue prepares the budget for a project:
They negotiate the budget with relevant people
Formal approval may be required
It will be a separate project-specific budget
Notes: Trainer explains where budget for projects are initiated and paid for by the venue will:
Be developed by the venue, that is, the budget will be set as a result of discussions and negotiations involving:
  The Board and/or relevant Committees and/or sub-committees
  Managers and owner/s
  External professionals such as those with expertise in accountancy, financial planning, and taxation
  You, as the PM/person responsible for the project: so your input about what might be required can be factored in to their thinking
Need to be formally approved by designated person/s within the business
Appear as a separate budget specifically for the project with its own budget code.
Class Activity – handouts
Trainer obtains, distributes and discusses sample budgets.

## Slide 49: Evaluate financial viability
Your role in preparing project budget may involve:
Attending budget meetings
Estimating costs
Determining contractor and provider availability
(Continued)
Notes: Trainer states as PM/person responsible for the project responsibilities in relation to assisting in the preparation of the budget for a project may involve:
Attending budget/financial meetings convened by management or relevant Committees/Sub-committees
Contributing relevant input from your knowledge and experience as it relates to the focus of the project, including researching data from previous similar projects conducted at the venue
Estimating costs based on experience, current quotations, estimations: see later slides
Determining availability of contractors, consultants and providers/suppliers, including calculating how ‘lead time’ may impact on costs: for example, you will always pay a premium where the project is urgent and conversely where you prepared to wait a while, providers will usually accept a lower price for the goods and services they supply

## Slide 50: Evaluate financial viability
Providing source material
Obtaining quotations
Developing list of preferred providers/suppliers
(Continued)
Notes: Trainer continues identifying PM role in budget preparation for projects:
Providing source material and information to others for their consideration as part of the budget planning process. This will relate to the provision of a quite diverse range of topics such as:
  Cost prices obtained from third-party providers
  Copies of information brochures
  Samples of goods
  Background/support materials (such as recommendations from others, results of independent research)
  Letters of support and recommendation from others
Obtaining quotations. It is standard procedure to obtain multiple quotations for ‘significant’ items/expenditures.
  Most venues require three quotations.
Developing a list of preferred providers/suppliers based on your personal experience, existing preferred suppliers used by the venue, and input from industry contacts who have used these businesses and recommend them
Class Activity – Handouts
Trainer obtains, distributes and discusses samples/examples of source material identified on the slide.

## Slide 51: Evaluate financial viability
Determining labour costs
Ensuring all costs for the project are identified
Providing feedback, comment and input
(Continued)
Notes: Trainer continues identifying PM role in budget preparation for projects:
Determining labour costs for project sub-sets where in-house staff are to be used. This involves determining:
  The hours to be worked
  Number of staff required including back-filling requirements, if applicable
  Using correct pay scales to calculate full labour costs (that is, ensuring calculations factor in all applicable on-costs which may include holiday pay, penalties, sick pay, higher duties allowances)
Ensuring all costs are identified and addressed. This is difficult to do for a ‘new’ project of the type never before undertaken by the venue.
  A brainstorming session with other supervisors and/or staff to identify costs, reference to previous project documentation (budgets, invoices), use of industry contacts and/or use of an external professional are ways to identify all costs. Where Work Breakdown Structures have (see section 1.8) been developed this will help determine cost types
Providing feedback/comment to management on input and information provided to you by eligible stakeholders such as customers, previous personnel at the venue who have PM experience, executives from industry associations, inspectors from government authorities
Providing feedback to management regarding the relationship between ‘quality’ and costs. In the same way there is a link between ’time’ and cost, so too is there normally a link between quality and cost: you get what you pay for.
  Decreasing expense generally results in:
  A reduction in quality of products
  A reduction in service standards
  An extension of time required to complete the project/work.

## Slide 52: Evaluate financial viability
Determining potential impacts of delays
Identifying amount and timing of payments required for the project
Evaluating terms and elements of applicable contracts
Notes: Trainer continues identifying PM role in budget preparation for projects:
Determining the possible impacts of delays to the project in terms of (as applicable):
  Increased overheads
  Finance costs
  Penalties provided for under contractual agreements
  Service delivery to guests and customers
  Revenue
Identifying amount and timing of payments required for the project. This can have major implications for funding of the project and alignment of contractual arrangements with projected venue cash-flow. Payments may relate to:
  Deposits payable to builders to commence work
  Progress payments throughout the project at nominated times/stages
  Final payment on completion/sign-off of work
Evaluating or reviewing pertinent elements of applicable contracts such as:
  Terms of trade
  Guaranties
  Warranties
  Terms and conditions in contracts
  Penalty clauses and penalties

## Slide 53: Evaluate financial viability
When determining the budget, consider:
Labour
External professional bodies/businesses
General overheads
Preparation and planning activities
(Continued)
Notes: Trainer explains a critical aspect of determining the budget for any project is to ensure all costs have been taken into account identifying there may be a need to consider:
Labour, including (as appropriate):
  Recruitment and selection costs associated with developing necessary project/team members and operational and support staff
  Wages/remuneration for the duration of the project – including all relevant aspects of the project which can be expected to include:
    Planning and preparation time
    Set-up time
    Backfilling
    Attendance at meetings
    Project implementation
    Project finalisation
    Standard on-costs
    Incentives and rewards (where appropriate/applicable to staff involved in the project)
  Staff training and development
External professional bodies/businesses to be used as project providers, suppliers, builders, security, entertainment, risk assessors, consultants. This includes payment for advice, payment for contracted work to be done, payment for goods and services to be provided
General overheads directly associated with the project
Preparation and planning activities such as visits to other sites to view facilities, meet with other Project Managers, meet with suppliers, meet with clients and undertake project research

## Slide 54: Evaluate financial viability
Technical and other support required
Administration support
Physical resources required
(Continued)
Notes: Trainer continues identifying considerations when preparing project budgets:
Technical and other support required. This can include:
  IT support
  Support from external event managers for entertainment and bands, sound and lighting, and firework displays
  Legal advice
  Financial expertise
  Procurement expertise
Administration support – see ‘Secretariat’ later slides
Physical resources. This can include the food and beverages for a function, as well as plant and equipment, machinery, furniture, fixtures and fittings for any other project.
  If the project was to refurbish a dining area the physical resources would reflect this specific need and be fundamentally different to the resources required if the project was to refurbish the guest rooms, the kitchen or the lobby.

## Slide 55: Evaluate financial viability
Compliance requirements
Contingencies
Required profit and revenue
Notes: Trainer continues identifying considerations when preparing project budgets:
Compliance requirements. Specifically this entails meeting legally imposed compliance requirements which may relate to technology, licensing, certification and safety.
  Special attention must be paid to ensuring all project staff have current certification to permit them to undertake nominated activities as imposed by the requirements of relevant legislation.
Contingencies – an amount is commonly included to cover the possibility of contingencies actually occurring
Profit and/or revenue where the project is intended to generate profit or revenue for the venue separate figures for these must be included as part of the cost.
  For example the refurbishment of a restaurant or guest rooms may generate revenue through selling the old tables, chairs and beds. A figure estimating the money this is expected to generate should be included.
Class Activity – Internet research
Trainer asks trainees to visit http://www.brighthub.com/office/project-management/articles/54894.aspx, read the article/s and discuss same.

## Slide 56: Evaluate financial viability
Estimating costs:
These are ‘educated guesses’
There will always be cost increases over the life of a project
Increases may be 10% – 25%
Never believe there will be no cost increases when estimating costs
Notes: Trainer discusses estimating costs for budgets:
Estimates of cost to be included in a budget are rarely little more than educated guesses.
Every project, regardless of the planning undertaken, is subject to cost increases.
  Even situations where a fixed price contract is signed with a supplier can be subject to increases in terms of penalties or additional work required that was not specified in the initial contract.
It has been found on the basis of experience any estimation of cost for a project budget should be subject to a 10% - 25% loading/variance to cater for ‘contingencies’, price rises, unexpected issues arising, delays and so forth.
The higher your level of confidence in the cost estimate, the lower the variance/loading should be, but it should never be zero.

## Slide 57: Plan and create administrative structure
Projects can benefit from an administrative structure but not all small projects need one.
Need can be identified from the following:
Direction from management
Mandatory pre-requisite from funding body
Personal experience
Willingness of others to participate
Internal policies and procedures
Notes: Trainer states where the scope and nature demands, it is necessary and advisable to create an administrative structure for the project mentioning many small projects do not require an admininstative structure.
Trainer explains the need for an administrative structure can be identified as a result of one or more of the following:
Directive/instruction from management for their to be such a structure
Pre-requisite requirement from a funding body for an administrative structure to be established to oversee and monitor the project
Your experience, relating to the need you see for a formal structure and a formal support structure
Willingness of others to be part of the project
Need to align with standing internal protocols, policies and procedures.

## Slide 58: Plan and create administrative structure
Benefits of creating an administrative structure for a project:
A committed reference source
A sounding board for your thoughts
Ready access to assistance
(Continued)
Notes: Trainer explains potential benefits of developing an administrative structure for a project:
A committed and dedicated source of support and advice
A sounding board for your thoughts and proposals
Ready access to assistance

## Slide 59: Plan and create administrative structure
Group to whom you can delegate project work
A reporting framework
Decision making hierarchy
Group to help with project responsibilities
Notes: Trainer continues explaining potential benefits of developing an administrative structure for a project:
An established body of people to whom tasks and responsibilities may be delegated
A formal reporting framework
A hierarchical structure for decision making
The ability to allocate project-related responsibilities and tasks to nominated persons or bodies.

## Slide 60: Plan and create administrative structure
Composition of administrative structure may include:
Management
Secretariat
Consultants
Contractors and suppliers
Groups
Steering committee
Notes: Trainer identifies possible composition of administrative structure for a project:
Management
Secretariat
Consultants
Contractors and suppliers
Groups
Steering committee.

## Slide 61: Plan and create administrative structure
The presence of Management in administrative structure enables:
Them to obtain first-hand experience of you and the project
Prompt authorisation for action you need to take
Provision of extra information and insight
Them to influence others who you want to influence
Notes: Trainer illustrates roles/responsibilities of administrative structure.
Management
A suitable management (or owner) representative should always be part of administrative structure so they can:
Gain first-hand experience of the management of the project and your activities in managing it
Promptly authorise action which needs to be taken outside your specified scope of authority
Provide extra information and insight to the project as the need for them to do so arises
Use their authority to influence others both within the organisation and external to it.

## Slide 62: Plan and create administrative structure
‘Secretariat’:
Provides administrative support for the project
Usually comprises existing office staff who work on project duties as required or directed
Notes: Trainer illustrates roles/responsibilities of administrative structure.
Secretariat
A ‘secretariat’ provides administrative support for the project.
The secretariat is often existing ‘office staff’ who take on extra project-related duties.
Class Activity – Question
Trainer asks students what activities might the Secretariat perform when providing administrative support for a project.
Possible answers:
General office work
Typing – letters, reports, emails, requests for quotations, RFTs, RFPs, agendas for meetings, minutes of meetings
Filing
Photocopying
Making telephone calls
Scheduling meetings, notifying people of meetings, distributing required information prior to meetings, preparing rooms/venues for meetings and taking minutes of meetings
Maintaining documentation
Facilitating communications
Processing payments and paperwork

## Slide 63: Plan and create administrative structure
Consultants:
Provide specialised professional advice
Are paid on a fee for service basis or an agreed sum
May provide input:
At meetings
Face to face
By phone
Online
Notes: Trainer illustrates roles/responsibilities of administrative structure.
Consultants
Consultants are businesses external to the business who provide specialist advice, suggestions and recommendations.
They are paid an hourly rate or an agreed sum for their participation and contributions to the project.
Their advice maybe provided:
  Face to face – to you personally
  At project meetings
  Over the telephone
  Online.
Class Activity – Question
Trainer asks students what type of consultants may be required to work on a project.
Possible answers:
Interior designer where rooms are being decorated/refurbished
Commercial catering consultants for kitchen upgrades/renovations
Safety consultants for a special event e.g. pyrotechnics display
Language and diversity/cross-cultural experts where a project involves people from a variety of different language, social, economic, religious or other backgrounds.

## Slide 64: Plan and create administrative structure
Providers and suppliers are chosen via a selection process:
Suitable businesses (pre-selection) are identified
Goods and services to be provided are specified
Samples and quotations are obtained
Participation expected is stipulated
Final decision is made
Notes: Trainer illustrates roles/responsibilities of administrative structure.
Contractors and suppliers
These are the businesses who will provide the goods and services which are at the heart of the project.
Generally the following selection process applies:
  A pre-selection occurs. For example you identify all the businesses who may be able to provide a certain product or service and then you determine which one will be part of the administrative structure. It is not usual for there to be two businesses representing the one type of product or service. The organisation is required to keep the information they learn while participating in the project ‘confidential’ . They may be required to sign a ‘confidentiality agreement’ to this extent
  The goods and/or services they are expected to advise on and provide are specified and quantified
  Sample products/services are evaluated/assessed
  Quotations are obtained
  The participation expected of them is stipulated, for example:
    To attend XYZ meetings
    To work cooperatively with nominated other contractors, suppliers and/or government agencies
    To provide items which are ‘fit for task’ – meaning they are safe, reliable, compliant with all relevant legislation and match any samples/examples provided for examination/inspection as part of the decision making process about what items to purchase
    To be available to provide telephone and online support at all times
  A decision on which provider/supplier is made based on quotations, quality, and responses to other criteria.
Class Activity – Question
Trainer asks students what type of products and services may providers and suppliers provide to a project.
Possible answers:
They may range from architects and builders through to carpet and paint suppliers to those who sell tables, chairs and the flowers to decorate the rooms.

## Slide 65: Plan and create administrative structure
Groups may include:
Advisory groups
Reference groups
Consultative groups
Notes: Trainer illustrates roles/responsibilities of administrative structure.
Groups
The administrative structure may feature the use of one or more types of ‘groups’ which may be called:
Advisory groups
Reference groups
Consultative groups.
These groups are not a necessary part of the administrative structure for all small projects but are beneficial in some instances especially in situations where it is important to:
Liaise with others especially those external to the organisation
Demonstrate consultation with others
Allow others to make input
Capture a wide range of thoughts and opinions
Generate 360˚ feedback
Encourage others to buy-in to the project and accept it.

## Slide 66: Plan and create administrative structure
Steering Committee may:
Provide oversight for the project
Review project progress
Give guidance
Notes: Trainer illustrates roles/responsibilities of administrative structure.
Steering committee
A steering committee is also not a common part of most small projects.
A steering committee comprises representatives from the groups identified above and its role is to help ‘steer’ the project to a successful conclusion. It does this by:
Providing oversight of the project
Reviewing the progress of the project against approved plans and targets
Giving you guidance on all manner of topics which may arise as part of your management for the project . For example you may turn to the steering committee (or members of it) for advice and direction in relation to areas in which the committee members have considerable experience and acknowledged expertise in areas such as:
  Company rules, requirements, policies, procedures and protocols
  Legal issues
  Industrial relations
  Finance and budget
  Acquisitions
  Marketing.
Depending on how the role of the steering committee is developed or interpreted by your employer, it may have:
  An advisory role only
  Total control over the project meaning it has the capacity/authority to take over the project from you if it believes this is necessary for whatever reason.

## Slide 67: Allocate project responsibilities
Factors impacting allocation of project responsibilities:
Composition of the administrative structure
Members of project team
Project-specific plans and strategies
(Continued)
Notes: Trainer states the identified responsibilities for any project need to be allocated to the relevant person and/or business so the project will achieve the required outcomes/objectives highlighting the basis for allocating project responsibilities relates to a combination of factors each of which can be expected to be unique for each small project.
These factors are:
The composition of your administrative structure and the expertise and experience whish is available from this source
The people who comprise your project team in most cases these are your main support structure as they are (usually) solely dedicated to the project where other support structures (including those in your administrative structure) will contain people whose time is shared between you, your project and many other obligations
The plans and strategies which have been developed for the specific project as these will identify what needs to be done

## Slide 68: Allocate project responsibilities
Known strengths and weaknesses of individuals
Those who have volunteered or indicated willingness to participate
Instructions from management
Personal development for individual staff
Requests from relevant bodies or agencies
Notes: Trainer continues identifying factors which will influence allocation of project responsibilities:
Known strengths and weaknesses of those available to you, including their previous experience and demonstrated capacity to perform and achieve outcomes
Staff who have indicated to you they wish to be involved and want to develop knowledge and experience in the area of project management or in the field to which the project applies
Direction given to you by super-ordinates who may order you to involve certain people or organisations, or may tell you to involve certain people in nominated activities
Your objective of developing a certain staff member to take over your position (in terms of succession planning) when you move on, or to increase the capacity for small project management within the business by multi-skilling staff who may become PMs in their own right or may serve as your deputy/assistant
Requests from delegating bodies, clients or funding bodies that certain people within the organisation are included in the project to undertake specified roles.
Class Activity – Excursion
Trainer arranges visit to a venue so students can:
Attend a project-related meeting
Observe activities within the meeting
Listen and observe what is covered and discussed.

## Slide 69: Allocate project responsibilities
Communicating allocation of responsibilities:
Determine preferred communication method for all involved
Identify format and content
Develop ‘Distribution List’
Notes: Trainer discusses the need to communicate allocated responsibilities identifying the following basic requirements need to be identified:
Preferred communication method for individuals – how people want/prefer to receive their information: not all preferences will be able to be catered for
Formats and content of communications determining in your own mind the sort of information which might be contained in different types of communications
Distribution List – identifying those who will receive communications, for each communication type.

## Slide 70: Allocate project responsibilities
Tips to optimise clear communication:
Plan the communication
Write/speak succinctly
Use only ‘known’ language
Only communicate when you have something to say
(Continued)
Notes: Trainer provides advice to facilitate clear communication when communicating with staff/project team:
Plan the communication – work out what you want to say
Write/speak succinctly – avoid unnecessary words
Use only words and terms known to the recipients – if you need to use a new word or term then make sure you explain it
Only communicate when you have something to say – avoid communicating when you have nothing to say

## Slide 71: Allocate project responsibilities
Allocate sufficient time to the task
Be prepared to ‘explain’ what you have to say
Monitor receipt of communication
Be respectful
Notes: Trainer continues providing advice to facilitate clear communication when communicating with staff/project team:
Allocate time for the communication – do not rush it
Be prepared to explain what you have said – let others know you are available to provide explanations or other clarification
Set up a system so you know people have received the communications you have sent them
Avoid terms or words which are offensive, disrespectful or discriminatory in any way.

## Slide 72: Allocate project responsibilities
Methods of communication:
One on one meetings
Group meetings
Telephone
Email
Memos
Notes: Trainer identifies the following will enable effective communication of project-related responsibilities:
Scheduled, one on one, face to face exchanges which is arguably the best method to use but it very time-consuming
Scheduled, group meetings which saves time but may stifle discussion of points which need to be discussed
Telephone communication
Email
Memoranda.

## Slide 73: Allocate project responsibilities
Project management tools can be used for:
Planning
Managing and monitoring
Sequencing tasks for the project
Budget control
Project evaluation
Most small projects do not use project management tools.
Notes: Trainer advises a variety of Project Management tools exist and can be used to:
Plan the project
Manage and monitor the project
Sequence project activities/work
Control the budget
Evaluate the project.

## Slide 74: Allocate project responsibilities
Examples of project management tools:
Cost/Schedule Control System
Critical Path Method
Gantt charts
(Continued)
Notes: Trainer identifies project management tools:
Cost/Schedule Control System (C/SCS)
Critical Path Method (CPM)
Gantt charts
Class Activity – Internet research
Trainer facilitates student access to the following (and similar) websites and discussion of findings:
Cost/Schedule Control System (C/SCS)
http://www.hyperthot.com/pm_cscs.htm
http://www.defence.gov.au/dmo/esd/evm/DefAust5655.pdf
Critical Path Method (CPM)
http://en.wikipedia.org/wiki/Critical_path_method
http://www.netmba.com/operations/project/cpm/
Gantt charts
www.ganttchart.com
http://en.wikipedia.org/wiki/Gantt_chart
http://www.mindtools.com/pages/article/newPPM_03.htm

## Slide 75: Allocate project responsibilities
Life Cycle Cost Analysis
Logistics support analysis
PERT charts
Project Management Software (PMS)
Notes: Trainer continues presenting and discussing project management tools:
Life Cycle Cost Analysis (LCCA)
Logistics support analysis (LSA)
PERT charts
Project Management Software (PMS).
Class Activity – Internet research
Trainer facilitates student access to the following (and similar) websites and discussion of findings:
Life Cycle Cost Analysis (LCCA)
http://www.treasury.nsw.gov.au/__data/assets/pdf_file/0005/5099/life_cycle_costings.pdf
http://www.eed.state.ak.us/facilities/publications/lccahandbook1999.pdf
Logistics support analysis (LSA)
http://www.logisticsworld.com/logistics.htm
PERT charts
http://en.wikipedia.org/wiki/Program_Evaluation_and_Review_Technique
Project Management Software (PMS)
http://en.wikipedia.org/wiki/Project_management_software
http://en.wikipedia.org/wiki/Comparison_of_project_management_software

## Slide 76: Plan communications, PR and marketing
You should involve the following in planning communications for a project:
Appropriate colleagues
Persons from outside the business
Notes: Trainer advises in any workplace activity ‘communication is key’ and this also applies to project management identifying those involved in planning communication for a project should include:
Appropriate colleagues
  Senior management as identified by the property for the project
  Departmental or divisional managers especially from ‘Marketing’/’Sales and Marketing’
  Project team members.
Persons from outside the business
  Clients who are funding a project (function/event)
  Representative from any delegating authority – if applicable
  Representative from any funding authority – if applicable
Class Activity – Guest Speaker
Trainer arranges for relevant PM to attend and discuss project communication with students.

## Slide 77
Planning internal communication for a project should determine:
How communication will occur
Frequency of communication
Report dates
(Continued)
Plan communications, PR and marketing
Notes: Trainer discusses internal communication stating:
Internal communication refers to communications which will occur within the venue.
This is communication from you to your project team and administrative structure, and from others working in the business to you and/or members of your project team and administrative structure.
The planning process should determine:
  How communication will occur
  Frequency of communication
  Dates for reports to be published

## Slide 78
Topics for communication
Protocols
Formats
Filing requirements
Distribution Lists
Plan communications, PR and marketing
Notes: Trainer continues discussing internal communication identifying what should be determined:
Topics for communication
Communication protocols
Formats for written communication
Filing requirements for all communications
Development of internal Distribution List.

## Slide 79
External communication may be required with:
Those on the Distribution List
Government agencies
Media
(Continued)
Plan communications, PR and marketing
Notes: Trainer states:
External communication refers to communications which occurs between you and those outside the business.
External communication may be required with:
  Nominated stakeholders as identified on the Distribution List
  Government agencies/authorities
  The media

## Slide 80
Nominated target markets
Locals
Suppliers
Consultants
Contractors
Plan communications, PR and marketing
Notes: Trainer continues identifying targets for external communication:
Nominated target markets as a whole, or specific (high-value/VIP customers) from within each target market
Local residents/the local neighbourhood
Suppliers and providers
Consultants for the project
Contractors engaged for the project.

## Slide 81
Extra factors in planning communication:
Person who will distribute communications
Person to be ‘contact’ for the project
Communication budget
Media to be used
Dates for communication events at the venue
Plan communications, PR and marketing
Notes: Trainer explains the planning process for communication should address the topics already listed for ‘internal communication’ plus:
Nomination of one person to be responsible for distributing the communications
Nomination of one person to be responsible as the ‘contact point’ for external enquiries
Budget
Names of media to be used
Host venue events/occasions where those on the external Distribution List will be invited to the venue.

## Slide 82
Public Relations = PR:
Relationship between venue and its ‘publics’
Intention is create a positive relationship
PR strategy explains how you will do this..
Plan communications, PR and marketing
Notes: Trainer introduces PR strategy for projects stating:
Public relations is the relationship that exists between the venue and its different ‘publics’: these publics may be the media, government authorities, suppliers, local neighbourhood community and all the different target markets the venue has.
The intention is to generate good public perceptions of the venue and for the project.
The PR strategy will identify how you intend achieving the goals you have set for PR in relation to the project.

## Slide 83
Goals of your PR strategy:
Provide information
Liaison and interaction
Responding to queries and complaints
Involving others
Plan communications, PR and marketing
Notes: Trainer presents possible goals for PR strategy:
Providing identified people and organisations/bodies with information. This can be in relation to:
  A series of information releases
  Specific information ‘points’ throughout the project such as start of the project, achievement of milestones, project completion
Liaising and interacting with nominated groups or individuals by way of (for example):
  Meetings and consultations
  Feedback sessions
  Visits/guided tours of the venue/project
  Developing and publishing reports
Responding to their questions, concerns and complaints in a variety of ways:
  Email
  Telephone
  Meetings
  Provision of information
Involving them in what is happening through regular contact, mail-outs, meetings, press/media releases.
Class Activity – Guest Speaker
Trainer arranges for relevant PM to attend and discuss PR strategies for projects with students.

## Slide 84
Planning your PR strategy:
Identify who you want a relationship with
Construct database
Define objectives
Determine media to be used
Prepare and distribute media release and project kits
Plan interviews with media and visits to venue/project
Plan how to track media and public sentiment
Plan communications, PR and marketing
Notes: Trainer identifies planning for PR strategy:
Identify who you want to influence/communicate with
Construct a database of their contact details
Define the objectives you want to achieve
Determine the media to be used
Prepare and distribute media releases and/or project kits for the media
Plan media interviews and visits to the venue
Work out how you will track/monitor media and public responses to your project.
Class Activity – Exercise
Trainer identifies a project and asks students to prepare media release for the project.

## Slide 85
Marketing strategy for project:
Activities to promote the venue and generate sales
Activities involved in market research and analysis
For small projects the focus will be ‘promoting the venue/project’ (as opposed to ‘selling’)
Must support venue marketing plans
Plan communications, PR and marketing
Notes: Trainer introduces marketing strategy for projects:
Marketing may be seen as the activities undertaken by the venue to promote and sell the products and services it provides.
Marketing also embraces a range of market research and analysis activities.
In this context (for small projects) a marketing strategy will usually emphasise ‘promotion’ rather than ‘sales’.
A marketing strategy supports/underpins attainment of the marketing plan/s of the venue.
Class Activity – Handouts
Trainer distributes and discusses examples of:
Project communication strategy
Project PR strategy
Project marketing strategy.

## Slide 86
Possible goals for a project marketing strategy:
Providing advice and information
Developing and distributing brochures and other promotional materials
Creating and lodging advertisements
Engaging in publicity
Website presence
Capturing project-related data and feedback
Plan communications, PR and marketing
Notes: Trainer explains goals for a marketing strategy can include:
Providing advice and information to clients, funding bodies and stakeholders
Developing and distributing brochures, fliers and other marketing materials
Creating and lodging paid advertisements
Engaging in publicity for the venue/project. Publicity is a sub-set of public relations as is advertising which is generally not paid for by the business
Including project information on the website of the business
Capturing data from identified groups or individuals relating to the project

## Slide 87
Tasks in planning marketing strategy:
Generate ‘information packs’
Create promotional content
Generate and maintain database
Determine locations for advertisements
Integrate project marketing with other venue initiatives
Plan communications, PR and marketing
Notes: Trainer explains planning tasks for marketing strategy:
Generate information packs to be sent to stakeholders/nominated persons
Create the content for brochures and other promotional materials
Generate a database of those to whom information needs to be communicated
Determining locations and frequency/schedule of paid advertisements and other unpaid promotional activities
Confirm your marketing activities integrate with other marketing activities being undertaken by the venue.

## Slide 88: Reach agreement on evaluation
Reaching agreement on evaluation:
Requirements may be imposed on you
Requires you to communicate with stakeholders
May require final approval of methods by management or stakeholders
Notes: Trainer explains part of the planning process for a project must be consideration of how the project will be evaluated once it has been competed identifying reaching agreement on evaluation methods and associated factors for small projects:
Be directed about the evaluation to be employed that is, management or a funding body will tell you what is going to apply and you have no say in it.
  In this case there is really no sense of ‘reaching agreement’. It is more a matter of making sure you understand what is being imposed on you.
Speak to relevant stakeholders at a meeting/workshop or series of these and:
  Seek their advice on the most suitable evaluation options
  Ask them to identify appropriate evaluation techniques
  Work collaboratively with them to produce evaluation methods which synthesis and reflect their orientations
Be required to submit your agreed evaluation to management or delegating authorities to gain their approval.
Class Activity – Guest Speaker
Trainer arranges for PM to attend and talk to students about:
How they determine evaluation methods for projects
Methods used
Those involved in determining evaluation methods.

## Slide 89: Reach agreement on evaluation
Agreement should be gained on:
Timing issues
Methods to use
Criteria for evaluation
(Continued)
Notes: Trainer states agreement should also be sought on the following evaluation-related issues:
Timing of the evaluation – when it is to take place
Evaluation methods to be used – see below
Criteria for evaluation – identifying what the project will be evaluated against: this should focus on the objectives and goals contained in the project management plan.

## Slide 90: Reach agreement on evaluation
Questions to be answered
Team members
Reports required
Distribution List
Notes: Trainer continues identifying topics on which agreement needs to be reached when discussing project evaluation methods:
Questions to be answered. This identifies specific questions which may be part of, or additional to, the goals and objectives for the project
Evaluation team members identifying who will be involved in the evaluation process
Reports (if any) to be generated outlining the contents to be addressed
Distribution List for sharing/communication results/outcomes and ‘lessons learned’ as identified by the evaluation.

## Slide 91: Reach agreement on evaluation
Reasons to identify evaluation methods:
To indicate project priorities
To enable generation of necessary evaluation tools
To develop good relations with those involved
To enable non-project related issues to be addressed
To verify the methods used will be appropriate to the objectives of the project
Notes: Trainer presents reasons why evaluation methods need to be identified:
The evaluation methods agreed on will indicate priorities for aspects of the project. You will, of course, spend more time and effort on elements of the project you know are going to be evaluated
This knowledge allows you to generate the necessary materials, evidence or data which will be required in the evaluation process
Knowing who will participate in the evaluation should indicate people with whom you need to establish a sound/positive working relationship
Sometimes the focus for evaluation is not contained in the scope and/or objectives for the project. It can sometimes be the case those evaluating the project intend evaluating topics you has not considered/been aware of
The evaluation method/s chosen must reflect the requirements of the project. Different projects will require different types of evaluation and even where similar evaluation methods are used, the specifics will normally require some form of change/fine tuning.

## Slide 92: Reach agreement on evaluation
Project evaluation:
All projects should be evaluated
Extent of the evaluation should reflect the project
Evaluation involves analysing and assessing the outcome measured against the criteria for the project
Notes: Trainer discusses evaluation of projects:
All projects should be evaluated.
The extent and degree of the evaluation should reflect the size of the project. Small projects should have smaller evaluations than major projects.
For large/major projects a formal ‘evaluation plan’ may be produced but this is not usual for small projects.
Evaluating a project means analysing and assessing the outcome of the project measured against identified criteria established before the project commences.

## Slide 93: Reach agreement on evaluation
Evaluation options:
Surveys
Questionnaires
Workplace observation
Piloting
Capturing qualitative and quantitative data
Notes: Trainer presents evaluation options:
Conducting surveys – talking to ‘relevant persons’ about the implementation and outcome/s of the project. Surveys should:
  Be structured so all those surveyed are asked to respond to the same questions
  Allow free space for respondents to add issues of their choice
  Surveys may be conducted one-on-one, or feature the use of group surveys of focus groups.
Applying questionnaires to nominated people. These may be paper-based or online questions posed to solicit input and feedback about the project
Workplace observation relating to project implementation and note-taking to provide a basis for later analysis
Engaging in pilots for aspects of the project. This features implementation of actual workplace trials of project elements to determine effectiveness, and reactions and responses from those who are impacted (such as clients, customers and staff) as well as funding bodies and delegating authorities
Capturing and analysing quantitative workplace data and qualitative data to identify changes which have flowed as a result of the project so these can be compared against projections: note that ‘baseline data’ must first be established for every aspect of data which is to be analysed.
  Quantitative data relates to ‘figures and numbers’ (know also as ‘hard data’) such as sales, profit, percentages, ratios, units and other information which can be presented in statistical form.
  Qualitative data (known also as ‘soft data’) refers to how people feel about the project, why they think what they think about the project and issues relating to how the project has impacted them.
Class Activity – Exercise
Trainer describes a project to students and asks them to develop a questionnaire to capture evaluation information.

## Slide 94: Develop project management plan
Project management plan:
Hard copy plan
Reflects size of the project
Differences in plans occur in relation to:
Detail
Complexity
Stages included or listed
Notes: Trainer introduces project management plan:
This is a hard copy plan setting out how the requirements for the project (scope and limitations) will be accommodated to achieve the identified project deliverables.
These plans reflect the size of the project. Small projects have small plans and bigger projects have bigger plans.
While the content of both are similar differences often occur:
  In ‘the detail’– more expensive projects have more detail
  In complexity – bigger projects are commonly longer in duration which introduces a level of complexity not found in shorter-term projects
  Stages and/or activities – bigger projects require more work to be done. The more work there is, the more planning needs to be done.

## Slide 95: Develop project management plan
Role of project management plan:
Gives clear understanding of project
Provides basis for management to review/approve project
The approved plan gives legitimacy to the project
Demonstrates ‘due diligence’
A useful tool for others to use in future project planning
Notes: Trainer discusses role of project management plan:
The project management plan enables you, and others involved in the execution of the project, to gain a clear and comprehensive understanding of the project (especially the objectives/deliverables, constraints [cost, resources, time]) before work on any aspect of the project actually commences.
It is standard procedure for the plan to be presented to management/the Board (or a relevant sub-committee/steering committee) for consideration and approval. They may question the plan and/or alter it as they see fit.
If you prepared the project plan they will expect you to present, explain justify and defend it at a presentation to them.
When the Board (or whoever) finally approves the project management (relatively few, if any, of these plans receive approval to proceed ‘as presented’) known as ‘signing off on the plan’. This gives you official permission to carry out the work as stated in the plan as ‘signing off’ also signifies the identified resources are/will be made available to you for the project.
Doing a project plan is also a good ‘due diligence’ step, providing evidence of the care you took in preparing and planning for the project.
This Plan can also by you (or others) to assist them in development of future project management plans.
Class Activity – Guest Speaker
Trainer arranges for management-level person to attend and talk to students about:
Role of project management plan
What they require in a project management plan
The approval process for plans.

## Slide 96: Develop project management plan
Reasons to prepare project management plans:
Avoids confusion
Provides authority and legitimacy
Guards against project creep
Provides basis for action
(Continued)
Notes: Trainer gives reasons to prepare project management plans:
Help avoid confusion about the work to be done. It gives clarity about all aspects of the project and removes doubt about what needs to be done and what does not need to be done
Provide ‘authority and legitimacy’ to the project. Once approved, it is an ‘official’ document which lends weight to it and helps you (as Project Manager) implement what it requires
Guard against project creep
Produces the basis for effective and efficient project execution

## Slide 97: Develop project management plan
Sets work priorities
Obviates reworking of tasks
Indicates interdependency of tasks
Avoids duplication and unnecessary expense
Informs the project team
(Continued)
Notes: Trainer continues giving reasons to prepare project management plans:
Set priorities for the work to be done by allocating sequential work order
Obviate the need to re-work things once project work has actually commenced
Indicate the way in which there is a need for cooperation and interdependency between, for example, people and departments involved in the project
Avoid unnecessary duplication of activities, effort and expenses
Put all project staff ‘on the same’ page about what needs to be done

## Slide 98: Develop project management plan
Provides basis for monitoring and evaluation
Creates a vital communication tool
Facilitates risk management
Assists with decision making
Optimises likelihood all project issues will be identified and considered
Notes: Trainer continues giving reasons to prepare project management plans:
Provide an essential document to use for monitoring, review and evaluation purposes
Provide a vital communication tool for stakeholders in relation to the project
Facilitate risk planning and management
Prescribe outcomes that can be used as the basis for guiding decision making throughout the project. This, in part, helps provide a context for decision making
Optimise the likelihood everything that should be thought about and considered regarding the project is, in fact, identified and given the necessary attention. With a project management plan there is a less chance of important/costly things being overlooked.
Class Activity – Handout
Trainer distributes and discusses sample project management plan.

## Slide 99: Develop project management plan
Disadvantages of project management plans:
They take time
May limit flexibility
May cause excessive focus on the ‘small things’
Notes: Trainer give disadvantages associated with preparing project management plans:
They take time. Some will argue they take too much time especially where the timeframe for completion is short and the nature of the project is very small
  The danger, people will argue, is too much time is ‘wasted’ on planning that should be used for ‘doing something’.
  In some venues you may have no choice in this regard as there may be a policy requiring you to prepare a project management plan,
A project management plan limits flexibility. Many people feel their ability to make decisions ‘on the run’/as things unfold or emerge is severely limited by the need to conform to a project management plan.
  Arguably this is not a severe limitation as the basis for all plans must be they are ‘set in jelly and not in concrete’: the plan must be flexible to accommodate unforeseen issues and eventualities.
Significant effort can often be expended focussing on the minutiae of the project with the danger being the focus on the bigger picture is lost or distorted.

## Slide 100: Develop project management plan
Contents of project management plan:
Name or title of project
Name of those who prepared plan
Start and finish dates
Stages of the project
(Continued)
Notes: Trainer identifies contents of project management plans:
Name/title of the project. Every project should have a definite name/title to readily differentiate one project from another
Name of the person/s who prepared the project management plan and date it was presented for consideration/approval.
  This provides a reference point in the event someone wishes to query of clarify an aspect of the plan
Start and finish dates. These should apply to:
  The overall project
  Stages of the project
Identified stages of the project, describing them in words (which identify the action required and/or the final outcome for the stage) and providing start and finish dates.
  These ‘stages’ should also contain a set of supporting actions (sub-steps) to be taken to achieve the desired outcomes.
  These stages are the ‘activities’ which need to be undertake. All activities must be allocated to one or more persons/businesses who responsibility for their completion.
  When all the listed stages have been completed, the project has been finalised.

## Slide 101: Develop project management plan
Major stakeholders
Risk identification
Milestones
Resources
Limitations
(Continued)
Notes: Trainer continues identifying contents of project management plans:
Major stakeholders by name, contact details and reason they are regarded as stakeholders
Risk identification and management/controls for those identified risks according to standard risk management procedures already undertaken.
  Note: it is standard for risk management to take place prior to the development of project management plan as this is often an essential element in determining the viability of the project.
  If risk management has already been done, the plan may include risk management activities (risk identification, risk assessment and development of risk controls).
  See later slides for more information.
Milestone information and dates – see later slides
Resources for the project – identifying specific resources (staff, physical resources, information) to achieve the project deliverables
Limitations and constraints applicable to the project

## Slide 102: Develop project management plan
KPIs
Allocation of responsibilities
Budget
Reporting requirements
(Continued)
Notes: Trainer continues identifying contents of project management plans:
Key Performance Indicators for use at Milestone dates and on completion of the project to help determine whether or not the project is proceeding according to schedule
Allocation of responsibilities to specific person/s for nominated action/s as identified within the Plan and its Stages
Budget. This should detail:
  Total money available with information regarding how this may be spent/what it is to be spent on (and often what is cannot be spent on)
  Contributions from contributing sources such as clients, agencies, the venue, head office, joint-venture partners, project sponsors
Reporting requirements indicating:
  Type of report – for example, inception report, progress report, and final report
  Format of report – verbal, or formal written report
  Distribution list

## Slide 103: Develop project management plan
Consultation strategies
Quality Assurance (QA) requirements
Communication
Tendering and selection process
Project evaluation
Notes: Trainer continues identifying contents of project management plans:
Consultation strategies which may indicate:
  Those with whom consultation is required
  The nature of these consultations
  Frequency or number of consultations necessary
  Information required from such consultations
QA requirements – specifying, for example:
  Standards and criteria to be applied to the project and project deliverables
  Qualifications of those used in the project
  Relevant compliance requirements imposed by any QA scheme used by the venue
Internal and external communication for the project – see later slides
Details of any tendering or selection process required, for example for):
  Selecting contractors and consultants
  Determining providers/suppliers to be used
  Purchasing nominated products or services
Details relating to evaluation of the project – identifying those involved, dates and requirements for evaluation of the completed project.

## Slide 104: Develop project management plan
Work Breakdown Structure:
Assists with project planning
Can be time consuming
Must address all aspects of the project
Must avoid work not covered by the project
Notes: Trainer introduces Work Breakdown Structure:
A concept that can be used to assist with project planning
  It is not mandatory, but can help make sense of projects by providing the mechanism for breaking them down into smaller, more manageable sub-sets or Stages (also referred to in project management terms as ‘discrete work elements’)
Is quite time consuming
Important points to remember when using WBS are:
  ‘The 100% rule’ – meaning the activity must cover all the requirements (100%) of the project
  The 100% rule also means actions outside the scope of the project must not be covered
  There must be no overlap/duplication between elements of the project in terms of their attribution in the WBS.
Class Activity – Internet research
Trainer facilitates students in accessing the following sites and engaging in discussion of information discovered:
http://www.hyperthot.com/pm_wbs.htm
http://www.anticlue.net/archives/000964.htm

## Slide 105: Develop project management plan
Planning and preparation for communicating the project management plan:
Arrange forum
Determine date and time for meeting
Notify those who need to attend
Follow-up
Arrange catering
(Continued)
Notes: Trainer discusses planning and preparation activities prior to communicating the project management plan to relevant persons:
Arrange a forum for the meeting – a nominated room
Arrange a date and time – in consultation with those who are required to attend
Notify those who need to attend – using their known communication preference
Follow up with those invited/required to attend – to encourage their attendance
Arrange catering – tea, coffee, water

## Slide 106: Develop project management plan
Plan the presentation
Distribute materials in advance
Follow-up after the meeting
Notes: Trainer continues discussing planning and preparation activities prior to communicating the project management plan to relevant persons:
Plan the presentation – this is vital.
  Your competency as PM will be inferred from the way you make the presentation. You need to:
    Determine content for the presentation
    Identify the sequence in which information will be delivered
    Choose method of delivery
    Generate supporting materials for handouts
    Prepare PowerPoint slides
    Arrange guest speaker (manager, owner, client – as appropriate) to present aspects of the presentation
Distribute materials in advance of the meeting as and where appropriate to allow/encourage people to pre-read them, identify issues they will need explaining and develop appropriate questions they want to ask
Follow up after the meeting with those who did/could not attend, and with those where extra information was to be provided.
Class Activity – Guest Speaker
Trainer arranges for experienced PM to attend and:
Talk to students about:
  Importance and role of project management plan
  Communication of the plan
Provide sample project management plan and discuss same.

## Slide 107: Develop project management plan
When communicating project management plan:
Distribute and explain all plans
Provide and explain budget information
Identify lines of communication
State lines of responsibility
(Continued)
Notes: Trainer identifies what needs to be included when communicating project management plan:
Distribution and/or explanation of all project-related plans. Standard practice is to ask project team members to treat these (and all other documents provided) as ‘commercial in confidence’. In this context may relate to:
  Project management plan
  Communication plan
  Risk management plan
  Marketing plan
Budget data covering types of resources available; amounts; budget and other codes; how to access resources; requirements for making purchases on behalf of the venue for the project
Preferred lines of communication for project activities to facilitate and optimise communication
Lines of responsibility as they apply for the project: these are often different to what normally applies so they need to be addressed/explained

## Slide 108: Develop project management plan
Describe delegations of authority
Identify accountability
Provide contact details
Explain all aspects of the plan
(Continued)
Notes: Trainer continues identifying what needs to be included when communicating project management plan:
Delegation of authority for the project including delegation of tasks, responsibilities, roles
Accountability for allocated duties
Contact numbers and details – extension numbers, mobile phone numbers, fax numbers, pager numbers, email addresses
All aspects of whatever is contained in the project management plan for the project. This can include coverage of attendant/sub-plans, timing requirements and/or constraints, resources, outcomes, objectives and deliverables, KPIs, reporting requirements

## Slide 109: Develop project management plan
Explain emergency response management plans
Address health, safety and welfare issues
Specify your role as PM
Indicate ‘open door’ policy
List scheduled meetings
Notes: Trainer continues identifying what needs to be included when communicating project management plan:
Emergency response plans for the project detailing what they cover, responsibilities, drills, trigger points for action
Health, safety and welfare issues. A project will often raise additional/different issues requiring standard risk management attention. This may mean certain issues need:
  To be investigated by designated people or agencies
  Job Safety Analysis sheets and procedures prepared for them
  Specific on-site safety training
  Provision and use of designated safety clothing and/or equipment
Your role as PM identifying what you will be doing/what staff can expect from you in terms of assistance, supervision, monitoring, oversight, decision making, and general support and liaison.
A declaration regarding your ‘open door’ policy should be made
Identification of scheduled project meetings. This should cover timing/location of regular/scheduled project meetings and emphasis on the role of these meetings and the importance of the need to attend these.

## Slide 110: Develop project management plan
Communication of project management plan can occur:
Face to face
By email
Using the phone
At a staff meeting or briefing
Notes: Trainer identifies how communication of the project management plan may occur:
Face to face meeting. This is the best option as it allows better follow-up to occur, incorporates non-verbal communication into the process and enables project team members to meet other project team members
Email may be useful to supplement face to face meetings, for example, where extra information needs to be disseminated
Telephone can be useful for contacting team members who could not attend the scheduled main meeting. This can be the case where part-time or casual staff from the venue are included as team members but cannot attend the initial induction meeting due to work or other commitments
Staff meeting/briefing. For small projects, the daily staff briefing/meeting can double as the induction meeting for project staff.

## Slide 111: Develop project management plan
Risk management comprises:
Risk identification
Risk analysis
Risk control
Notes: Trainer discusses risk management in relation to projects stating it comprises a three-step process:
Identify risks – a structured process to determine all applicable risks as they apply to the project
Analyse/evaluate risks – also known as risk appraisal which involves identifying and comparing options for controlling the identified risk
Control the risks – applying the most effective control options identified in the risk analysis process.
Class Activity – Guest Speaker
Trainer arranges for experienced PM to attend and talk to students about:
Risk identification for projects
Risk analysis procedures
Examples of risk control used for projects.

## Slide 112: Develop project management plan
Project risks may be classified as:
Project-specific
Staff-related
Funding/financial
Outcome/performance risks
Environmental
Technological
Legal
Notes: Trainer discusses how risks may be classified:
Project-specific risks relating to issues effecting, or likely to be impacted by, the project
Customer risk – risks faced by customers as a result of the project being undertaken in/at the venue: health, safety and welfare considerations are critical here to ensure the safety of all patrons
Staff risks – risks faced by staff who are participating in delivering/servicing the project: again, health, safety and welfare considerations are important and attention should be paid to investigating how the project increases/changes the hazards staff might normally encounter
Funding/financial risks relating to, for example, cost over-runs, unforeseen/unexpected expenses, failure of financial institutions to provide funding as arranged, promised or expected for the project
Outcome/performance risks relating to issues where project deliverables are not being (or, have not been) provided as required/anticipated.
Environmental risks which may address possible pollution issues arising from noise, air, water and/or waste disposal
Technological risks which may arise if the wrong ‘system’ is used/purchased.
  This may relate to ensuring an out-dated system is not purchased; ensuring the purchase of a new system /equipment will integrate with existing systems or will integrate with other systems to be bought/needed in the future
Legal risks relating to issues where the venue fails to comply with legislated requirements and/or breaches enforceable contractual provisions.

## Slide 113: Develop project management plan
A risk management plan should be prepared which should:
Identify and describe all identified risks
List risks into a risk register
Allocate a code to each identified risk
Notes: Trainer states a risk management plan should be developed which should:
Identify and describe the risk comprehensively and accurately (insofar as this is possible) using qualitative description (defining and describing the risk) and quantitative description (attaching figures, numbers, statistics to the risk)
Place each identified risk into a project-specific Risk Register
Give each risk a code/number to help locate it on the internal venue system. This code can also be used as the basis for further action, funding and reference purposes
Class Activity – handout
Trainer distributes and discusses a sample risk management plan for a project.

## Slide 114: Develop project management plan
Calculate ‘likelihood’ for each risk
Determine severity of ‘consequence’ for each
Identify rating for each risk
Develop controls
Notes: Trainer continues identifying contents of a risk management plan:
Calculate the likelihood of each identified risk occurring in descriptive terms such as ‘Very likely’, ‘Likely’, ‘Unlikely’ or ‘Very unlikely’
Determine the severity of the consequence of each identified risk if it occurs. This may be in statistical terms or ‘Major’, ‘Serious‘, ‘Minor’ or ‘Insignificant’
Tabulate the likelihood and consequence of each risk to determine its rating such as ‘Low’, ‘Medium’, ‘High’ and ‘Extreme’
Develop coping/control mechanisms to be adopted by the venue to address each identified risk – see later slides.

## Slide 115: Develop project management plan
Ways to identify risks for a project:
Refer to previous venue history and information
Talk to others at the venue
Use your personal experience
Paying a consultant
Using project-specific techniques and/or project software programs
Notes: Trainer identifies ways to identify risks for a project:
Experience and previous history
This involves:
Gathering together staff who have worked on previous similar projects and seeking their input regarding risk management. It is really useful to speak to previous Project Managers.
If previous PMs have left the venue, try to find out where they are now and talk to them
Speaking to management (and other relevant stakeholders – internal and/or external) about their recollections regarding previous projects
Analysing documentation within the business to identify lessons learned such as reading previous contracts, project reviews and evaluation reports and results
Conducting Brainstorming sessions to identify possible risks.
Formal investigation
This can include:
Paying for the services of a professional, external project management business who have experience (a) with this type of project, and (b) the hospitality industry.
Using fault-tree analysis (FTA) and/or Fishbone (Ishikawa) diagrams. These are techniques used to help identify possible causes for a risk and relate these possible causes to each other and the projected result/outcome of the risk eventuating (linking cause and effect).
Software programs can be used to assist with these. It is not recommended you use these approached unless you have previous experience with them, or unless you have someone to help you who has previous experience with them.
Class Activity – Internet research
Trainer asks students to visit and discuss their findings for:
http://en.wikipedia.org/wiki/Fault_tree_analysis
http://www.mindtools.com/pages/article/newTMC_03.htm

## Slide 116: Develop project management plan
Possible generic responses to identified risks for projects:
Risk avoidance
Accepting and controlling risk
Transferring risk
Deferring risk
Limiting risk
Notes: Trainer identifies possible generic responses to identified project risks:
Risk avoidance – that is, not proceeding with the project
Accepting and controlling the risk – taking action to alter either the likelihood of the risk occurring, and/or reducing the consequence of the risk if it does occur
Transferring the risk which involves taking out appropriate insurance to cover the project, and/or outsourcing all/most of the work to reduce the liability/exposure of the organisation
Deferring the risk – postponing the project till a later date
Limiting the risk – only proceeding with part of the original project proposal.

## Slide 117: Develop project management plan
Contingency plans:
May be mandatory for your project, may not be
They are ‘Plan B’
Provide direction when problems occur
Will be prepared as part of the risk management process
Notes: Trainer discusses contingency plans for projects:
Your project may require you to prepare/consider ‘Contingency plans’ for your project.
Contingency plans are ‘Plan B’.
They govern what could/should be done when a situation arises where the initial plans cannot be implemented and/or the actions to be taken when an identified risk actually occurs.
The factors uncovered as part of risk management will determine to a great extent what the contingency plans cover, and how extensive they are.
Not all projects – especially very small, very short-term projects – have contingency plans prepared.
Risk management plans and Contingency plans should be included as part of the formal project management plan. Some venues may establish a Risk Register to assist with detailing and recording specifics of identified risks.
Class Activity – Handout
Trainer distributes and discusses sample project contingency plans.

## Slide 118: Identify key project milestones
Milestones:
Points where nominated activities are expected to be completed
Occur throughout a project
Have no standard length or timelines
Allow monitoring of the project
Notes: Trainer introduces ‘milestones’ stating:
Milestones are points in time when nominated activities are expected to be completed, or times when important decisions need to be taken about subsequent action/work.
Milestones occur at significant points in the project such as the end of a stage (or combination of stages) for a project.
They can be seen as project checkpoints or benchmarks.
There is no standard timeline for the setting of milestones. The key factor in determining when/where they occur are an estimation of the time required to achieve completion of the work which has to be undertaken. This means:
  Some milestones are much longer or shorter than others
  Multiple milestones can occur at the same point in the project.
Setting milestones allows you to monitor the actual progress of the project against projected/anticipated progress of the project.
Milestones should follow/reflect the flow (order/sequence) of the activities required to compete the project and may be allocated:
  A number – such as ‘Stage 1’, ‘Stage 2’ and so on
  A written descriptor such as ‘Tenderers and Consultants researched, identified and contracted’, ‘Fixtures and fittings removed and room prepare for fit-out’.
In most cases the achievement of one milestone indicates the start of another one.

## Slide 119: Identify key project milestones
When identifying milestones:
Know start and finish dates for project
Identify all work to be completed
Involve others in the process
(Continued)
Notes: Trainer states milestones should be identified as part of the planning process for the project explaining when identifying milestones:
Ensure you know the start and finish date for the project. These are the two parameters within which all milestones must fit
Make sure you have identified all work which needs to be undertaken to complete the project. This work will need to be converted to Stages which often form the basis for a milestone
Verify you have scheduled the required work in the proper sequence as milestones reflect the progressive nature of the project.
  Where subsequent work/action relies on work being completed, the milestones for the previous milestones must precede the later ones.
Involve others in assisting identify the Stages of the project and the milestones which should apply, asking others to contribute always helps ensure correct sequencing/scheduling of activities and helps make sure nothing is over-looked in the planning process. This requirement is especially applicable to:
  Contractors
  External providers
  Consultants

## Slide 120: Identify key project milestones
Include penalty clauses
Seek approval from stakeholders
Look for ‘logical’ breaks
Set a date before milestone date to check progress
Many PMS have a ‘Create a milestone’ facility
Determine related meetings, inspections and reports in advance
Notes: Trainer continues explaining requirements when identifying milestones:
Include penalty clauses applicable to external providers/contractors if they fail to meet milestone requirements and ensure they sign-off on these
Seek approval from key stakeholders for the milestones you have tentatively identified
Look for logical ‘breaks’ in the project which automatically qualify as obvious milestones
Set a date before the milestone is due as an inspection or check date where you examine actual progress against the requirements of the upcoming milestone giving you time to take whatever remedial/catch-up action is needed to attain the requirements of the milestone
Realise many PMS systems have a ‘Create a milestone’ facility and this may be useful to you
Determine the meetings, inspections and/or reports which must attach to each identified milestone.
Class Activity – Handout/s
Trainer distributes and discusses a range of sample milestones which may attach to small projects.

## Slide 121: Identify key project milestones
When communicating milestones:
Ensure relevant dates are fully understood by others
Send ‘advanced notice’ of milestone dates to others
Provide copy of project management plan with milestones to all concerned
Detail exactly what each milestone comprises
(Continued)
Notes: Trainer explains when communicating milestones attention must be paid to:
Ensuring the applicable dates are understood by everyone. They should be encouraged to diarise them.
You should also send out advanced notice about them as the date approaches to remind people.
Giving each relevant person a project management plan with the milestones for which they have responsibility highlighted
Detailing exactly what each milestone comprises so there is surety about what should be completed

## Slide 122: Identify key project milestones
Advise people of action to take if their milestones will not be completed on schedule
Notify people of flow-on impacts on not meeting milestones
Check the budget as part of checking milestones
Notes: Trainer continues identifying aspects to which attention must be paid when communicating milestones:
Advising people of action to take when/if they believe milestones they have responsibility for will not be completed by the scheduled date
Notifying people of the flow-on implications of milestones not being achieved as specified and by the time specified
Checking the budget as part of the process of checking milestones.

## Slide 123: Summary – Element 1
When planning project:
Make sure you know the scope and objectives
Determine the project deliverables
Consult widely with stakeholders and relevant others
Identify resources required and prepare a resource strategy
Determine the financial viability of the project as part of standard operating procedure
(Continued)
Notes: Trainer provides a recap of the Element asking questions to check trainee understanding and responding to questions from trainees, as required.

## Slide 124: Summary – Element 1
Develop an administrative structure for the project
Manage your time effectively
Allocate responsibilities for work to be done
Undertake risk management activities
Prepare a project management plan with contingency plans
(Continued)
Notes: Trainer provides a recap of the Element asking questions to check trainee understanding and responding to questions from trainees, as required.

## Slide 125: Summary – Element 1
Develop PR and marketing strategies appropriate to/if required for the project
Communicate and share plans with internal and external stakeholders
Consider use of project management software
Determine the methods to be used to evaluate the project
Notes: Trainer provides a recap of the Element asking questions to check trainee understanding and responding to questions from trainees, as required.

## Slide 126: Administer and monitor project
Performance Criteria for this Element are:
Implement and monitor project in conjunction with project team members
Provide support and assistance to team members, as required
Build trust and respect within the project team
(Continued)
Notes: Trainer identifies for trainees the Performance Criteria for this Element, as listed on the slide.

## Slide 127: Administer and monitor project
Assess and review progress against project goals and in consultation with project team members
Determine the need for additional project resources and take action accordingly
Monitor budget in accordance with enterprise guidelines
Provide regular reports on project progress to all appropriate colleagues/customers
Complete the project within agreed timelines
Notes: Trainer identifies for trainees the Performance Criteria for this Element, as listed on the slide.
Class Activity – Discussion
Trainer leads a general class discussion on administering and monitoring projects by asking questions such as:
What do you think is involved in administering and monitoring a small project?
Why are these activities necessary and important?
How could you provide support to project team members?
How might you build trust and respect with team members?
Why is there a need for progress reports for small projects?

## Slide 128: Implement and monitor project
Standard practice at start of a project:
Verify all requirements
Consider you personal workload:
Prioritise and/or delegate work
Create personal work schedule
Diarise your time
Meet with client
(Continued)
Notes: Trainer explains when the planning for a project has been completed and all necessary authorisations have been obtained, the next step is to start the project ‘proper’ highlighting from this point forward the extent to which the project succeeds or fails rests with this phase.
Trainer states it is where they have to ‘walk the talk’ (to put into practice the plans you developed and which have been approved) identifying standards practice at the outset is to:
Verify all requirements for project start have been met. You would for instance require:
  Copies of relevant authorizations which have been signed-off
  Direct approval from the manager/owner to proceed
Look at your own workload for the project period and take appropriate action to ensure you can commit the required time to the project, which may involve:
  Prioritising work
  Delegating work
  Creating a personal work schedule
  Diarising time you have committed to/for the project
Meet with the client to enquire if they have any final requirements additional to what is already known.

## Slide 129: Implement and monitor project
Communicate with other supervisors/managers
Convene meeting with staff
Notify staff of approval and start
Identify other projects your project can integrate with
Notes: Trainer continues identifying standard practice at start of a project:
Communicate with other supervisors and managers to advise them of the project and the fact it is about too start
Convene a meeting of your staff and team/s to brief them on the project and its commencement
Advise staff and project teams the project has been officially approved and notify them of any last-minute changes made
Identify any other workplace projects or activities which the project can – or should – be integrated with to achieve savings and other efficiencies.

## Slide 130: Implement and monitor project
To effectively manage a project:
Give it the attention it deserves
You need to be a physical presence
Facilitate the work of others
(Continued)
Notes: Trainer states without suitable management any project will quickly start to display signs of problems explaining effective project management demands:
Attention to project management. It sounds basic but it is so important.
  You must allocate sufficient time and focus to doing just this: ‘managing the project’.
  Project management must take priority and others in the venue (supervisors, managers, staff) have to realise this. You have to make them accept and understand your primary focus is the project (as well as completing other day to day you normally have responsibility for.
You are a constant physical presence. All projects benefit from the PM being present and available.
  ‘Being there’ encourages questions from people/organisations who are not sure about what to do.
  Being there demonstrates the importance you place on the project.
  Being there at all times allows you to see what is going on and intervene when things are not going according to what you know to be the plan/requirements.
  ‘Being there’ means being in/on the project work site – not being hidden away in an office somewhere.
  You can never successfully manage any project only from an office.
Facilitation of the work of others involved in the project whether they are internal staff/team members or external third-party providers, consultants or contractors. Facilitation can mean literally hundreds of things such as:
  Opening the venue early so workers can gain access
  Authorising entry to restricted areas
  Providing information as required to enable decision making
  Taking charge of a situation and making decisions about what can/cannot and should/should not be done
  Giving permission/authority to vary an approach, standard, timeline or deliverable
  Using your authority to prioritise conflicting or competing requirements of the venue and of the project

## Slide 131: Implement and monitor project
Provide constant monitoring of everything
Attend all project meetings
Foresee problems
Take notes – ‘Project notebook’
Effective time management
Take remedial action as required
Notes: Trainer continues presenting requirements for effective project management:
Constant monitoring of the project. This involves constant/regular evaluating and measuring of ‘actual’ progress against ‘projected’ progress as set out in the project management plan.
Attendance at all project meetings. As PM you are duty bound to be present at each and every project meeting. This means attending them regardless of when they are convened and regardless of other work you have to do.
  As soon as you miss just one project meeting regardless of how legitimate your reason/excuse for not being there is, others will misinterpret this as a lack of dedication and enthusiasm and their commitment to the project will begin to falter.
  This means you must attend all project-related meetings which may be called by the Board, stakeholders, staff, management, contractors, delegating authorities, committees without exception.
Ability to foresee potential problems and raise them with relevant others to address them before they convert into actual problems/issues.
  This ability must apply to scheduling problems/clashes, potential delays, labour issues, funding short-falls, procurement, delivery, installation and commissioning.
Constant note-taking . As PM you should make lots and lots of notes in your Project Notebook (see later slide).
  Never rely on your memory about things that happened; things that failed to happen; what was said (by way of a promise or commitment by another person) face-to-face or over the phone.
  Always write it down.
Trainer continues presenting requirements for effective project management:
High levels of time management – this is fundamental to any successful PM role.
  You must spend some time working out how you are going to spend your time – planning the use of your time is vital.
  There will never be enough time for you to do all you have to do (‘normal’ work plus project activities) and extra work will always emerge on an almost daily basis as the project progresses.
  Some tips to better manage your time include:
    Get to work earlier – and leave later. This may not be what you want to hear but it can be your reality for at least part of most projects
    Learn to say no – say ‘No’ to other work that is not part of the project: delegation is an effective tool in this regard
    Bundle similar tasks – this is basic time management at work stuff:
      Only read emails once or twice per day as opposed to every 30 or 60 minutes
      Write reports at the one time each day/week
      Hold all your briefings/meetings at the same part of the day – the meeting with staff could be at 3:45PM; meeting with the Manager at 4:00PM; meeting with suppliers and contractors at 4:30PM; meeting with the Board at 5:00PM
Taking of remedial action as required – sometimes this will require communication with others (internal and external) but often it is a matter of you making an on-the-spot decision to:
  Overcome a problem
  Direct staff about what to do, when and/or how to do something
  Solve a stalemate situation
  Approve/authorise a suggestion made to you by someone else
  Modify the project management plan.

## Slide 132: Implement and monitor project
Use a Project Notebook to record information obtained:
As you walk around the project
From others as ‘feedback’
From a phone call
Through a flash of inspiration
Notes: Trainer encourages students to use a Project Notebook to record information obtained:
By walking around the venue/project and observing what is happening
As verbal feedback from stakeholders
As a result of a telephone call with a stakeholder
As a flash of inspiration while working on the project.
Not all relevant details of a project can be captured using even the most extensive and comprehensive reporting and monitoring system so the project note book really is a vital tool.

## Slide 133: Implement and monitor project
Notes ‘taken at the time’ can be used for:
Formal reports and general reference
Clarification of issues
Detailing information given to project people
Determine action to be taken
Resource provision
Personal reminders
Notes: Trainer advises notes taken in the Project Notebook may be used later for a variety of reasons:
Formal reports
General reference
Clarification of options, conflicting ideas and suggestions and information received
Information disseminated to project team members
Determining action to resolve issues, delays and problems
Resource provision
Personal reminders of action that needs to be taken.
Class Activity – Handout
Trainer distributes and discusses sample Project Notebooks.

## Slide 134: Implement and monitor project
Keys to managing ‘quality’ elements of a project:
Make sure you know the required standards/criteria
Monitor quality as part of the monitoring process
Discuss and explain quality with providers prior to project start
(Continued)
Notes: Trainer states many if not most deliverables in a project have some form of quality criteria attached to them. These may be specified in the project management plan or simply be understood but un-stated and PMs are expected not only to ensure tasks are completed but completed to the required standards stressing keys in achieving this are:
Ensuring you know the quality standards/criteria for all aspects of the project. Remember the concept of quality is variable and often difficult to define but there is usually a strong link between the amount paid for a product or service and the level of quality received.
  The point being not all quality for a project will be ‘top’ quality. The project may specify a lower level of quality (for a cheaper price) that is still acceptable to needs.
Monitoring ‘quality’ as an important issue at every meeting with all stakeholders. This means letting them know you are concerned with quality and will be checking it.
  This helps avoid problems associated with quality caused by ‘near enough is good enough’ thinking.
Meeting with project team members, suppliers, contractors and similar prior to their involvement to explain quality requirements and to give them an opportunity to ask relevant questions/clarify expectations.

## Slide 135: Implement and monitor project
Conduct regular quality inspections
Make sure sub-standard work in redone
Refer providers to project management plan (and previous discussions) where there is a need to clarify quality requirements
Notes: Trainer continues presenting keys to managing quality in a project:
Undertaking regular quality inspections of work completed as opposed to simply allowing finished work to go unchecked.
  Providers tend to do a better job where they know their work will be checked, and know they will be asked to repeat/re-do sub-standard work.
  It is a good idea to undertake these inspections with the providers, staff and contractors so you can identify and discuss issues on the spot.
Ensuring all sub-standard work is re-done to the quality standard/criteria required by making sure all identified sub-standard work is fixed.
  One of the worst things that can happen in terms of quality is for the provider, staff or contractors to perform sub-standard work, know you have identified it as such, and find they are allowed to ‘get away with it’:
  This sends a message that you or the venue will accept ‘anything’ and their standard will drop to deliver similar poor quality across nearly all deliverables.
Referring contractors, project staff and others to the project management plan (and/or relevant contracts) where reference is made to quality standards/criteria so they can see for themselves what is required.
Class Activity – Handout
Trainer distributes and discusses sample project management plan with reference to specific quality requirements for the project.

## Slide 136: Provide support and assistance to team
Need to provide support and assistance to team:
To facilitate achievement of project deliverables as identified in project management plan
To demonstrate your commitment to the staff working on the project
To show your respect for those working on the project
(Continued)
Notes: Trainer emphasises a vital role when administering and monitoring a project is the provision of necessary support for project team/s presenting reasons/need for the provision of support and assistance as being to:
Enable/facilitate successful outcomes of project deliverables as approved by stakeholders and as identified in the project management plan and scope. Staff cannot deliver what is required unless they have the facilities and resources to perform the work
Demonstrate your commitment to the team members and the project and your commitment to the project
Show the respect you have for team members and the role they play in delivering the project: see also section 2.3

## Slide 137: Provide support and assistance to team
To help maintain project team enthusiasm for the project
To enable prompt advice and direction to be provided as required during the project
To show to management you are providing effective management of the project
Notes: Trainer continues presenting need for support and assistance of project team/staff/workers:
Maintain enthusiasm of team members towards the project
  A vital element of the support a PM can provide for a project/to project team members is to maintain personal enthusiasm for the project
Enable prompt advice and direction to be given where and when necessary so the project can proceed in a timely manner/without delay
Prove to management of the venue you are delivering appropriate management, supervision and over-sight of the project.
Class Activity – Guest Speaker
Trainer arranges for experienced PM to attend and:
Identify and explain administering and monitoring activities for project work
Describe techniques to optimise effective project management
Illustrate support and assistance a PM needs to provide to their project teams.

## Slide 138: Provide support and assistance to team
Examples of support and assistance which may be given to project team members:
Conduct a ‘project induction’
Provide promised resources as identified in the project management plan
Deliver promised or necessary training
(Continued)
Notes: Trainer gives examples of support and assistance a PM may provide to project team members:
Conducting a Project Induction (also known/referred to as ‘project start-up activities’) – a special meeting/briefing to explain the project, identify the resources, specific timelines, share the project management plan and allocate responsibilities
Actually providing the resources identified in the project plan and identified in the project induction. This can include:
  Providing codes or other information to enable/authorise team members to procure/access resources and/or information
  Providing formal authority to make purchases on behalf of the venue/project
  Providing internal authorities (codes, identification cards, keys) to enable access to areas, facilities, stores and other project-related areas/spaces
  Recruiting necessary staff – to fill identified/required roles
  Physically supplying resources to teams/team members, that is, handing things over
  Working with other managers/supervisors to arrange for release of venue staff from normal duties to participate in project work and facilitating back-filling where necessary
Provision of necessary/promised training and development for team members to enable them to do (or better do) their allocated tasks under the project plan.
  Training and development may be informal, in-house training or off-the-job, formal, accredited training.

## Slide 139: Provide support and assistance to team
Provide necessary project oversight
Schedule and conduct regular meetings
Motivate the team
(Continued)
Notes: Trainer continues giving examples of support and assistance a PM may provide to project team members:
Providing necessary, requested and/or promised project oversight by providing supervision, monitoring, coaching, direction and guidance
Scheduling and/or conducting regular project team meetings. Some projects require daily (or twice daily) meetings: one in the morning before work starts and the other at the end of the day/shift.
  A minimum should be at least one meeting per week otherwise there is too much disconnect between the team and the project. These meetings provide a forum for:
    Raising project-related issues
    General communication regarding satisfaction levels with progress, feedback on support being provided, changes being identified as the project progresses, and ‘issues arising’
    Identifying and resolving workplace health, safety and welfare matters
    Identifying and resolving team-related issues such as problems within the team, team composition, capabilities of the team, size of the team and relationship within the team and between the team and others.
Providing initial motivation to team members by explaining why the project is of value to the venue and stakeholders. You may refer to one or more of the following (as appropriate) as legitimate motivation:
  Enhanced job security for everyone in the venue
  Potential for increased earnings, more challenging work, deeper job satisfaction
  A safer workplace
  A more prestigious workplace/venue as a result of the success of the project
  Meeting what the competition is doing
  Leading the field in terms of the initiative that is the focus of the project

## Slide 140: Provide support and assistance to team
Give time to the team – talking to them and motivating them
Be ‘seen’ around the project
Maintain enthusiasm
Provide encouragement
Give feedback
Notes: Trainer continues giving examples of support and assistance a PM may provide to project team members:
Giving time to the team. This can occur in a number of ways
Being seen in the project area as a visible presence
  Spending time talking to project staff
  Helping them think through challenges and problems
  Sharing their successes and their disappointments in terms of project work
  Providing ongoing motivation
Maintaining enthusiasm for the project by, as appropriate or necessary
Providing ongoing encouragement to team members for effort as well as work done
Empathising and sympathising to show concern for individuals
Passing on comments/feedback from others including positive and negative
  Confirming for the team the progress they are making against plans and the KPIs and milestones
  Celebrating the achievement of project milestones.

## Slide 141: Build trust and respect with team
Reasons to build trust and respect with your project team:
Your success depends on the work of the team
It is the basis for the success of the project
If you help others achieve what they want, they will help you achieve what you want
Human resources are essential to achieve deliverables
Lack of trust and respect leads to project paralysis
Notes: Trainer gives reasons it is necessary to build trust and respect with project team:
You have to understand your success as PM rests very much on the work done by those who support you – you will be judged (by venue management and other stakeholders) on how well or how badly they perform their allocated tasks
Generating trust and respect is a fundamental platform/basis for attaining the identified goals/objectives for the project. This reflects the interpersonal nature of relationships in the workplace: if people do not like or respect you then this translates into the work thewy do for you
If you help others achieve their wants and goals then they are more likely to help you achieve yours – all workers want to be trusted and respected
Physical and financial resources are useless and irrelevant without the human resources needed to apply them
Where there is no trust there can only be fear and a lack of faith about what needs to be done to achieve the identified goals – fear leads to project paralysis and this will greatly impeded project success.
Class Activity – Guest Speaker
Trainer arranges for an experienced PM to attend and:
Highlight need to provide support and assistance to project staff
Explain need for trust and support between project team and PM
Illustrate how trust and respect between these two parties can be developed and maintained.

## Slide 142: Build trust and respect with team
Points to note about trust and respect:
It is a two-way street
It is essential
You cannot ‘tell’ someone to have trust and respect
You have to give trust and respect to the team
(Continued)
Notes: Trainer presents points to note about trust and respect:
Trust and respect is a two-way street – there must be mutual respect.
You must have trust and respect for your project team/s and they must have trust and respect for you
You cannot order or direct someone to have trust and respect
You have to give trust and respect to your team

## Slide 143: Build trust and respect with team
You have to earn trust and respect from the team
Trust and respect results from a combination of factors
Trust and respect are established over time
Notes: Trainer continues presenting points to note about trust and respect:
You have to earn trust and respect for yourself
Trust and respect is the result of a combination of factors such as:
Trust and respect are established over time.
Class Activity – Questions
Trainer asks students what factors combine/are needed to develop trust and respect.
Possible answers:
Honesty
Reliability
Credibility
Understanding
Commitment
Good communication
Consultation and collaboration

## Slide 144: Build trust and respect with team
Ways to build trust and respect:
Doing more than others
Not micro-managing
Valuing people
Getting to know the team
(Continued)
Notes: Trainer presents ways to build trust and respect:
Doing more yourself than you expect them to do. It is vital you lead by example and demonstrate your capacity for work
Avoid micro-managing them – give them a job and let them determine how to do it unless it has to be done in a certain way
Value each member of the team – see the project team as individuals rather than as a vague conglomerate of people
Get to know the people in the team – learn their names, about their likes and dislikes, their personal history and about their expectations

## Slide 145: Build trust and respect with team
Using staff names when talking to them
Communicating regularly
Giving encouragement and feedback
Giving responsibility
(Continued)
Notes: Trainer continues presenting ways to build trust and respect:
Use their names when talking to them. This demonstrates you have made an effort to get to know them
Communicate with all of them on a regular basis – keep the lines of communication open
Provide and encourage constructive feedback
Give them responsibility – nothing demonstrates trust or faith in staff better them actually placing trust in them to complete work which has been allocated to them

## Slide 146: Build trust and respect with team
Celebrating individuality
Doing hands-on work
Congratulating them when it is deserved
Not lecturing them if they make a mistake – adopt a ‘no blame’ policy
(Continued)
Notes: Trainer continues presenting ways to build trust and respect:
Celebrate the individuality of your team members – diversity can be a cornerstone of success
Pitch in and do some hands-on work yourself to contribute to the project as opposed to only be seen to undertake management duties: demonstrate your competency
Congratulate them regularly but make sure the congratulations are ‘earned’ and legitimate – congratulate them:
  Individually and face to face
  At team briefings and meetings
  When they have done good work
  When they achieve a KPI or milestone
If they make a mistake, do not lecture them – rather take a constructive approach and:
  Identify what went wrong – adopting a ‘no blame’ policy
  Explain or demonstrate the correct way
  Avoid being angry, vindictive or aggressive

## Slide 147: Build trust and respect with team
Encouraging input and opinions
Spending time with team in a special context
Never playing favourites
Address problems and issues promptly
Telling your manager about the good work done by individuals and/or the team
Notes: Trainer continues presenting ways to build trust and respect:
Encourage their input, opinions and feedback – never be afraid of listening to what team members have to say or contribute
Spend some time with them in a social context instead of only interacting with them in a work/project-related setting
Never play favourites. Avoid situations where:
  You spend more time with some team members than others
  You give ‘better’ jobs to some team members but not to others
  You discipline some team members but not others for the same issue
  You provide more opportunities to some but not to others
  You give more freedom or latitude to some but not to others
Address issues and problems promptly as opposed to ignoring them and allowing them to fester and grow
Advise your manager about the good work done by your team and/or individual members of the team. Make sure you never take credit for the work of others.

## Slide 148: Assess and review progress
Need to assess and review projects to:
Compare ‘actual’ progress against ‘expected’ progress
Provide basis for remedial action to be taken
Provide basis to give and receive for feedback
Allow integration of the project with other work
Notes: Trainer states PMs need to assess and review project progress to:
Compare actual progress against expected/anticipated progress such as:
  Allocating more staff or time to the project
  Providing additional resources – see later slides
  Changing suppliers or contractors
  Revising the project management plan to allow, for example, more time to complete stages or to include work which was not originally identified (or required by the client)
Enable accurate and honest feedback and reports to be given to you from the team and stakeholders on the project
Give your project team necessary feedback
Allow you to integrate other work/projects with your existing workload.

## Slide 149: Assess and review progress
Main aims of assessment and review process:
Confirm activities being undertaken
Identify activities which are behind schedule
Identify activities not attaining required standards/criteria
Determine remedial action
Notes: Trainer identifies aims of this process are to:
Confirm activities which are being achieved as planned
Identify activities which are running behind schedule or which present the potential to run behind schedule
Identify activities which are not achieving the required levels, standards or criteria
Determine action to be taken to bring the project back on track in terms of the project management plan and within the prescribed parameters for the project.

## Slide 150: Assess and review progress
Project management plan considerations:
Deliverables
Budget
Quality
Customer satisfaction
Use of resources
Notes: Trainer states assessment and review should address project management plan as well as issues arising highlighting points for consideration in the project management plan are:
Deliverables for the project in terms of what has happened (past events/work) and what can be foreseen (future project-related activities/outcomes):
  Are they being achieved?
  Are stages of the project running on track with the timelines set for them?
  Are milestones being achieved?
  Are future deliverables at risk?
  Why is this the case? What are the causal reasons?
  How will the current situation impact the rest of the project?
Budget. This should be addressed to:
  Check money has been spent as expected and only as authorized
  Verify the amount which remains in the budget
  Determine if the budget can realistically be expected to support/enable completion of the project
  Validate expenses have been allocated to correct budgets and budget lines
  Ensure expected income has translated into actual income
  Calculate the extent to which extra finance may be required, what it is needed for and why it is necessary
  Quality – the standards and criteria set for the project as part of the planning phase must be included in the assessment and review to:
  Verify the required standards are being achieved
  Determine any rectification work which has to be undertaken to retrieve outcomes which have failed to achieve the required standard
  Serve as a warning to providers/staff their work is actually being monitored
Trainer continues identifying topics for considerations in relation to project management plan when assessing and reviewing progress:
Customer satisfaction. This requires attention in terms of the following:
  Determining customer response/s to any interruptions or reductions to standard service provision caused by the project
  Determining customer satisfaction and response to any aspects of the project with which the guests/customers now have access or are experiencing (such as refurbished rooms, different workplace protocols, new facilities)
  Determining the extent to which the project outcomes at this stage have met their expectations
  Efficient use of resources which addresses:
  Verifying only necessary goods and services have been bought to ensure there is no excess purchasing of things
  Checking to ensure waste levels of goods and/or services is not excessive
  Monitoring the use of all resources (as identified in the project plan) are being used in accordance with stated need.
Class Activity – Handout
Trainer distributes sample project management plan which is used to demonstrate the assessment and reviews (as listed on the slide) which may take place.

## Slide 151: Assess and review progress
Also need to assess and review ‘issues arising:
Problems with third party providers
Difficulties with project work teams
Issues with client
Lack of cooperation
Involvement with external agencies
Notes: Trainer states assessment and review should also address ‘issues arising’:
Problems with third party providers such as them:
  Failing to perform work as promised or contracted
  Not finishing work by the required date
  Using sub-standard materials
  Imposing price increases
Difficulties with the work/project teams such as:
  Internal conflict within the team
  Other areas of the venue demanding team members work on other tasks
  Individual not being able to perform as expected
Issues involving the client/delegating body such as:
  Changing their mind about previously agreed arrangements
  Wanting more for the same money now you are committed to and have started the project
  Inability to communicate as and when needed with them to seek advice and direction
Lack of cooperation from internal sources such as:
  Other departments/supervisors not releasing the staff you want to work on the project
  Slow processing of requests such as purchase orders, requisitions, payments and general paperwork
Involvement of external agencies or authorities who may:
  Impose extra compliance requirements on the project as the project progresses and inspectors identify additional requirements they believe you must comply with.

## Slide 152: Assess and review progress
Ways to optimise effective project assessment and review:
Allocate time for the process
Plan meetings
Do your own analysis first
Work with others
Explain focus for each assessment and review
Allocate time and resources for the process
Remind team and stakeholders about why assessment and review needs to occur
(Continued)
Notes: Trainer presents and explains techniques to optimise effective assessment and review of project progress:
Schedule time for regular assessment and review. You must allocate time for this aspect of project management: never assume you will be able to ‘make time’ for it or that you will have enough time to undertake this activity
Plan meetings with the team and relevant stakeholders to discuss progress and advise them well in advance of when and where these will take place
Do your own analysis first before you participate in assessment and review with the team.
  You need to develop your own perspective on where things are at before you engage with others on this topic.
  Engage with the project team and other relevant stakeholders as part of the process.
  They will be able to contribute valuable insight and information and they need to be made aware of how you (as the one responsible for the project) have evaluated the progress.
Trainer continues presenting ways to effectively assess and review project progress:
Tell the team exactly what is the focus for this assessment and review so they are certain about the aim of the process and know what is not being considered.
  Make sure they have access to the agreed project management plan so they can refer to the topics being discussed and can see for themselves the targets//outcomes being considered were actually contained in the plan at the outset.
Make sure you have allocated sufficient time for this process and for all meetings which need to take pace as part of the process. These assessment and review meetings always take longer than you would expect. This is because:
  It is possible for different people to judge ‘progress’ in different ways. Not everyone sees progress in the same way: certainly your interpretation of progress is likely to be different to that of the team members to some extent regardless of how objective you try to be
  Team members can become very defensive when their work is criticized (no matter how sensitively you do it) and you need to spend some time supporting them and addressing personal issues which will emerge as a result
  There can be significant discussion and debate over the remedial action which needs to be taken to retrieve a situation which is ‘out of control’
  There are nearly always considerable contributions relating to the ‘issues arising’ part of the process
  Refresh the project team about why the assessment and review needs to occur so they understand the reasons for it and do not simply think you are ‘checking up’ on them and their work.
  Remind them they were advised this process was a standard part of your intentions for project management, and is not an indication something is wrong, you are displeased or the client is upset.

## Slide 153: Assess and review progress
Conduct workplace inspections
Using ‘actual’ evidence as basis
Advising team of implications of not attaining requirements of project management plan
Making the process a positive one for those involved
Notes: Trainer continues presenting ways to effectively assess and review project progress:
Conducting workplace inspections of project-related completed activities and activities in-progress with members of the project team so everyone can see the progress at the same time and there is therefore less uncertainty about:
  What has been done
  The quality of the work which has been done
  Physical problems which exist or can be seen as emerging
Using actual ‘evidence’ as the basis for the assessment and review. The aim must be to use objective proof as the basis for process. This will include:
  Conducting workplace inspections
  Making actual reference to relevant documentation as opposed to basing decisions/thoughts on memory
  Using actual statistics and data in order to make judgements as distinct from using half-truths and ‘beliefs’
Advising the team members of the possible implications if the plan cannot be achieved according to the plan prepared for it so they understand a lack of progress has consequences and they are well aware of what these might be
Ensuring the assessment and review process is a positive one for those involved.
  This can be difficult to achieve where it is obvious the project is behind schedule or otherwise failing to meet the deliverables set for it.
  This, however, underlines the need for you to plan the meeting so you can:
    Identify and draw attention to the positives which exist and there will always be some of these if you look hard enough
    Remain positive in your approach and demeanour. If you are down-beat and pessimistic this will rub off on the team
    Explain how the situation may be retrieved and brought back on track.

## Slide 154: Determine need for additional resources
Need to identify need for extra resources:
Must be done as soon as possible
Must occur across all resource types – human, financial, physical, time
Underpins achievement of deliverables
Demonstrates your PM expertise
Notes: Trainer presents requirements relating to need to identify need for extra resources:
As soon as possible. The quicker you identify these the more time you have to plan how to obtain them and to take necessary action to acquire them
Across all resource types. You must consider the potential need for human resources, financial resources, physical resources and time
To enable the project to achieve the objectives/deliverables. A lack of necessary resources always underpins all project failures and shortcomings
To demonstrate your effective management and oversight of the project.

## Slide 155: Determine need for additional resources
Options for obtaining more human resources:
Changing composition of project team
Taking staff off other duties to work on project
Hiring more staff
Training staff
Transferring funds in the budgets
(Continued)
Notes: Trainer presents options for obtaining more human resources:
Swapping the staff being used on the project with other staff who may be more productive
Taking staff off other duties and allocating them to project tasks
Engaging more staff
Providing training
Moving funds for staffing from a non-project budget line to a project-related labour budget line

## Slide 156: Determine need for additional resources
Monitoring hours worked by staff
Walking around the project site
Explaining to management how arising issues are impacting labour
Highlighting benefits which might flow from using extra labour on the project
Stressing downsides of not providing extra staff
Notes: Trainer continues presenting options for obtaining more human resources:
Monitoring the start and finish times of project staff – to ensure they are working the hours they claim they are working
Walking around the project site to provide a visible presence which allows motivates staff to apply themselves to their work
Showing management how the emerging needs of the project (which were not previously identified or factored into staffing requirements) are impacting the labour budget
Highlighting the benefits which may flow from increasing your allocation for labour. These benefits could include:
  Better productivity
  Quicker finish to the project
  Increased client and/or guest and customer satisfaction
Stressing/illustrating the down-sides of not providing extra staff such as:
  Reduced customer satisfaction
  Increased chance of penalties for non-discharge of contractual requirements
  Negative impact on image and reputation of the venue.

## Slide 157: Determine need for additional resources
Options for obtaining more financial resources:
Moving money between budgets
Seeking funding for requirements not identified as part of initial costing process
Seeking reimbursement from client
Ensuring deposits and payments are received
Reducing quality and/or quantity
(Continued)
Notes: Trainer presents options for obtaining more financial resources:
Moving money from another budget to the project budget if permitted
Seeking additional money on the basis of new requirements not previously identified when initial funding was applied for
Seeking reimbursement from clients for monies spent on their behalf for goods and services not agreed to as part of initial project agreements
Ensuring deposits and progress payments are being received as expected from the client/funding body
Reducing the quality and/or quantity of some aspects of the project to save money

## Slide 158: Determine need for additional resources
Selling old items
Obtaining lower prices from suppliers
Using a different acquisition option
Sharing the cost
Notes: Trainer continues presenting options for obtaining more financial resources:
Making sure all items which can be sold to generate revenue are indeed sold and not just disposed of
Sourcing different providers who can supply the same, or similar, goods and services at a lower price
Using different acquisition options instead of buying an item you may be able to better use your limited finance by hiring/renting items
Sharing the cost of items with other venues in the same organisation as you, or with other departments within the same venue.
Class Activity – Guest Speaker
Trainer arranges for management-level person to attend and discuss extra resourcing of projects in relation to:
Time
Human resources
Financial resources
Physical resources.

## Slide 159: Determine need for additional resources
Options for obtaining more physical resources:
Asking for loan items
Using fewer items
Using lower-quality items
Asking for contributions from your industry network of contact
(Continued)
Notes: Trainer presents options for obtaining more physical resources:
Asking suppliers, providers, manufacturers to loan you items or to donate items
Using fewer items within the project
Using lower-quality items which will be less expensive
Seeking contributions from your network of contacts

## Slide 160: Determine need for additional resources
Borrowing from other departments
Doing ‘contra’ deals
Asking client to contribute
Notes: Trainer continues presenting options for obtaining more physical resources:
Borrowing from other departments
Doing ‘contra’ deals where you:
  Swap a meal or similar at the venue in exchange for materials, goods and services from a supplier
  Receive free product in return from advertising the product/provider in the venue
Asking the client to contribute materials.

## Slide 161: Determine need for additional resources
To obtain more time for the project:
Explain how your time is currently being used – justify any claim for more time
Analyse your current use of your time
Delegate more
Defer non-essential work
Coming in earlier and going home later
Working smarter
Taking more time to plan what needs to happen – better planning usually results in better outcomes
Notes: Trainer illustrates possible action to obtain (or ‘create’) more time may include:
Explaining time already committed to the project to management to justify the claim for extra time
Analyse your actual use of time – perhaps using a time log
Delegating more work to other staff
Deferring non-essential work until after the project has been completed or until a nominated stage of the project has been achieved
Coming in to work earlier and going home later
Working smarter
Using technology and accepted time management techniques to save time
Taking time to plan your work – ‘make the plan, work the plan’.

## Slide 162: Monitor budget
Possible guidelines relating to budget monitoring:
Budgets format
Training required
Identification of budget types
Frequency of monitoring
Supporting documentation
Notes: Trainer presents examples of possible organisational guidelines for budgets:
Format of budgets used explaining:
  How they are laid out
  What the columns means
  Budget lines and codes
Training required before you are authorised to access and monitor any venue budgets addressing topics such as:
  Signs and symbols used – such as + and -, %
  Budget terminology
  Reading and understanding budgets – what they contain and what they mean
  Identifying variances
  Interpreting system flags/warnings
Identification of budget types such as differentiating between the roles and contents of budgets such as:
  Revenue budgets
  Labour budgets
  Purchases
  Overheads
Frequency for budget monitoring which may be:
  Daily
  Weekly
Supporting documents for different budget types. These are the source documents on which budgets are prepared/updated and include documents such as:
  Receipts for revenue
  Invoices for goods purchased
  Staff time sheets
Class Activity – Handouts
Trainer distributes and discusses sample enterprise budget guidelines.

## Slide 163: Monitor budget
Planning financial management approaches requires you to:
Access budget/financial plans
Clarify budget/financial plans
Negotiate changes to budget/financial plans
Prepare contingency plans
Notes: Trainer presents budget monitoring practices:
Planning financial management approaches
This can require PM to:
Access budget/financial plans for the work team
Clarify budget/financial plans with relevant personnel within the organisation to ensure that documented outcomes are achievable, accurate and comprehensible
Negotiate any changes required to be made to budget/financial plans with relevant personnel within the organisation
Prepare contingency plans in the event that initial plans need to be varied
Class Activity – Guest Speaker
Trainer arranges for accountant/bookkeeper to attend and talk to students about:
Enterprise guidelines for budget monitoring
Practices involved in budget monitoring
Identification of deviations
Contingency plans for budgets.

## Slide 164: Monitor budget
Implementing financial management approaches requires you to :
Disseminate relevant information to team
Provide support to team to enable financial management responsibilities
Determine and access resources and systems to manage finances
Notes: Trainer continues presenting budget monitoring practices:
Implement financial management approaches
This can require PM to:
Disseminate relevant details of the agreed budget/financial plans to team members
Provide support to ensure that team members can competently perform required roles associated with the management of finances
Determine and access resources and systems to manage financial management processes within the work team.

## Slide 165: Monitor budget
Monitoring financial activities against budget requires you to:
Check income and expenses against budget/s
Include financial commitments when monitoring
Identify deviations
Investigate deviations
Advise relevant persons of budget status
Notes: Trainer continues presenting budget monitoring practices:
Monitoring financial activities against budget
This can require PM to:
Check actual income and expenditure against budgets at regular intervals
Include financial commitments in all documentation to ensure accurate monitoring
Identify and report deviations according to organisation policy and significance of deviation
Investigate appropriate options for more effective management of deviations
Advise appropriate colleagues of budget status in relation to targets, within agreed timeframes.

## Slide 166: Monitor budget
Identifying and evaluating options for improved budget performance requires you to:
Assess costs to identify areas for improvement
Discuss issues with stakeholders
Undertake necessary research
Define and communicate benefits and drawbacks of new approaches
Factor in impact on customers
Present recommendations to management
Notes: Trainer continues presenting budget monitoring practices:
Identifying and evaluating options for improved budget performance
This can require PM to:
Assess existing costs and resources and proactively identify areas for improvement
Discuss desired budget outcomes with relevant colleagues
Undertake appropriate research to investigate new approaches to budget management
Define and communicate clearly the benefits and disadvantages of new approaches
Take account of impacts on customer service levels and colleagues in developing new approaches
Present recommendations for budget management clearly and logically to the appropriate person or department.

## Slide 167: Provide regular reports
Reports for projects may be required in:
Verbal form
Written form
Both
Notes: Trainer explains it is a standard requirement all projects are subject to some form of reporting requirements and these may be in:
Verbal form
Written forms
May be required to make a formal presentation of your report during which you can be asked questions by those in attendance (the stakeholders for the project), and expected to explain irregularities and shortcomings as well as justify decisions made and action taken.

## Slide 168: Provide regular reports
Report types:
Inception report
Progress reports
Final report
Notes: Trainer further explains reports may be required:
When the project commences – an Inception report
Throughout the project – known as ‘Progress reports’
On conclusion of the project – called a ‘Final report’.
The timing of these reports should be negotiated with stakeholders as part of the planning process so you know well in advance what your reporting obligations are.
Note that submitting required reports on the dates they are due is as important as completing the project in accordance with the timelines for the project.
Class Activity – Handouts
Trainer distributes and discusses samples of:
Inception report
Progress reports
Final report’

## Slide 169: Provide regular reports
Involve others when preparing reports, such as:
Client
Project team
Steering Committee
External providers and contractors
Other stakeholders
Notes: Trainer highlights need to involve others in the preparation of reports advising this means involving and seeking input and comment from:
The client
Your project team members
The Steering Committee
External providers and contractors
Any other body/organisation who have had significant impact on the project or who can be expected to have significant impact.

## Slide 170: Provide regular reports
Role of project reports:
Enables communication with stakeholders
Demonstrates openness and due diligence
Complies with mandatory project requirements (where they exist in this regard)
Provides material for future reference
Allows another opportunity for contact with stakeholders
Notes: Trainer explains role of project reports:
Enable communication with stakeholders regarding progress of the project including identification of issues arising, delays and their cause, and foreseeable problems.
  In this way reports look backwards at what has happened, and also looks forward to what may be expected to happen.
Help you demonstrate openness, due diligence, accountability, honesty, transparency and general management practices applied to the project
May be a term of the contract for a project that exists with, for example, a funding agency/authority
Provide hard copy information for future reference. The reports should be filed and form part of a growing body of information that can be referred to learn lessons
Allow another opportunity for you to talk to the stakeholders to express fears about the project, convey impressions about providers, identify concerns and give a general appraisal of the project across all relevant topics and issues.

## Slide 171: Provide regular reports
Reports will address:
Progress or attainment of outcomes
Budget
Input and feedback
Issues arising
Notes: Trainer identifies topics regularly addressed by reports:
The extent to which required outcomes as identified in the project plan have actually been achieved and, as applicable, the extent to which this area is behind or in front of the timelines. This is a central part of any report and focuses on the extent to which deliverables are being achieved. Comments in this part of the report should also address:
  Quality and quality-related issues
  Use of physical resources
Budget – identifying the money spent and percentage of allocated funds which have been spent.
  A copy of supporting documentation may be included as part of budget coverage
  Input/feedback from stakeholders regarding the project – such as:
  Identification of issues
  Complaints
  Compliments received regarding the project
  Issues suppliers/contractors believe have the potential to impact on deliverables
Issues arising –and issues of concern to you.

## Slide 172: Complete project
Possible actions to ensure the project is completed on time:
Conduct appropriate start-up activities
Schedule provision of necessary resources
Management procurement of resources
Check and validate all documentation
Monitor progress against the project management plan
Do more yourself
Ask other to do more
(Continued)
Notes: Trainer states a key requirement for any project is to complete it as intended within the required time lines identifying the following as possible actions which may need to be taken from start to finish of a project which will help complete the project on time:
Conduct appropriate start-up activities making sure all those engaged with the project know exactly what their roles and responsibilities are, and what your expectations are.
  The key is final project deliverables are based on initial understanding. You have to put in place this understanding at the start of the project.
  You cannot wait until the end of the project to do it, and you cannot wait until there is a problem before this is addressed.
  You have to start the project the way you intend it to be maintained.
Schedule the provision of all identified and necessary resources:
  Staff, contractors, sub-contractors – a primary task of any PM is coordination of resources
  Materials, products, systems, plant and equipment
  Funds, cash, credit
  Inspections and approvals to facilitate further work and the next tasks
Manage the procurement of resources to ensure required materials and other resources are available when needed.
  Lack of resources when needed is one of the biggest causes of delays to projects.
Check, validate and/or authorise all project-related documentation – especially anything relating to purchases/expenditure, certification of work completed and variations to contracts or plans.
  Making it a priority to be actively involved in these decisions and activities is key to knowing how the project is progressing and to quickly identifying potential problems, delays and cost over-runs.
Monitor progress of the project against the project management plan on a regular/daily basis to enable the earliest identification of problems.
Do more yourself – the reality of many projects is you will have to do a substantial amount of the work yourself.
  When things are running behind schedule this means you have to do even more.
Ask others to do more. Explain the ‘behind schedule situation’ and its implications and encourage/motivate others to do more, work harder or be more productive

## Slide 173: Complete project
Adjust plans as required
Conduct regular meetings with stakeholders
Report on the project
Maintain the project team
Negotiate extensions, if required
Be prepared to change project team roles and responsibilities
(Continued)
Notes: Trainer continues presenting actions which help ensure projects are completed on time:
Adjust plans as required. Rarely does any project reach a successful conclusion without the need for original plans to be altered.
  Your ability to smoothly accommodate the need for change in this regard will be a major indicator of your ability as a PM.
  You will be expected to make small changes on the spot and unilaterally – larger changes will need to be referred to the management, stakeholders or the Steering Committee for their input and approval.
Conduct regular meetings with stakeholders to discuss progress, enable their input, resolve issues, and maintain satisfactory relationships (which can prove beneficial when you have to ask for extra time or resources, or explain why the project is running behind schedule)
Report on the project as required by the project plan.
  This can help alert others to the possibility they need to assist with ensuring you can bring the project in on time.
  It is also possible those who receive and read your reports can provide advice about what to do to retrieve the situation.
  If you know you have to report, this can also serve as a motivator for you.
Maintain the project team. This can mean you need to address and resolve team-based issues, rotate staff through the project team, match staff to required competencies/abilities, maintain team harmony and support team dynamics.
Negotiate an extension of the deadline. This is arguably one of the most common responses to problems with a project but is not an option for projects such as functions/events.
  The potential for time overruns on a project is extremely high especially when the venue is relying on external providers/contractors to supply products and services.
  Given the enormous potential for events to impact on a project (such as supply problems further down the supply chain, weather, staffing issues, unforeseen problems, transport), this should come as no surprise, and is a major reason why those involved in developing contracts for projects will negotiate the longest possible time for completion.
Change roles and responsibilities within project team members to address interpersonal conflict situations, to address a situation where the existing team does not have the necessary skills/expertise to achieve the project deliverables

## Slide 174: Complete project
Outsource some of the work
Find a way to reduce costs
Seek more money
Look for more efficient methods and practices to complete the work which needs to be done
Notes: Trainer continues presenting actions which help ensure projects are completed on time:
Outsource aspects of the project. There can be times when you believe the venue can deliver on certain outcomes/deliverables, only to find in reality this is impossible.
  Perhaps staff are not skilled enough, perhaps they are too busy, or perhaps they have no real commitment to what needs to be done.
  Regardless of the reason, effective project management at times can mean engaging the professional services of an external third party to replace what you believed could be handled in-house..
  It is important for you to understand doing this is not an indication of your incompetence – rather it is testimony to your ability to recognise a problem and take appropriate action in response.
  If you had simply persevered with a situation which was obviously not working, then that would be an indicator of your incompetence.
Reduce costs on materials or physical resources so more money is available for labour to compete the project.
  Limited options for reducing costs include:
    Extending timelines – suppliers or contractors may be prepared to reduce costs if they have longer to deliver
    Lowering quality standards/criteria – this can mean accepting a lower quality in exchange for lower prices
    Negotiating discounts for prompt payment
    Sourcing alternative suppliers
    Revising project deliverables to enable/accommodate reductions in expenditure
  Always talk with suppliers/contractors to explain the need to cut costs and hope they are prepared to accommodate, at least to some extent, your requirements.
  It is a fact of life sometimes simply talking to a supplier can result in a 5% reduction to quoted prices.
Seek more money for labour from management or seek approval to make a budget line transfer to obtain extra labour funds
Research and apply more efficient methods for completing project tasks. There can often be a need to do this where:
  Safety and security is not an issue
  Unexpected problems have emerged
  Authorities have intervened and requested changes
  New/different standards, compliance requirements have emerged

## Slide 175: Complete project
Where remedial or other action needs to be taken in respect of a project, ‘communication is key’:
Communicate early
Communicate fully
Communicate to all who are involved
Notes: Trainer stresses whenever faced with a situation where remedial or other action needs to be taken in relation to a project, effective communication is vital:
Communicate early – communicate as soon as a potential risk/issue has been identified: never wait
Communicate fully – be honest, open and tell the complete story about the actual/potential risk
Involve all stakeholders – do not be selective: collaboration and consultation are vital.

## Slide 176: Summary – Element 2
When administering and monitoring project:
Make sure all preparation and planning has been completed
Verify you have authorisation to proceed
Know what the project management plan contains
Work the plan
Use a project notebook
(Continued)
Notes: Trainer provides a recap of the Element asking questions to check trainee understanding and responding to questions from trainees, as required.

## Slide 177: Summary – Element 2
Manage quality
Provide support and assistance to project team members as required
Build trust and respect with all stakeholders
Assess and review the project at regular points
Be alert to the potential for the project to require additional human, physical and financial resources as well as time
(Continued)
Notes: Trainer provides a recap of the Element asking questions to check trainee understanding and responding to questions from trainees, as required.

## Slide 178: Summary – Element 2
Respond promptly to identified need for extra resources
Monitor the budget and financial activities for the project
Report in accordance with the requirements of the project management plan
Take necessary action to complete the project on time
Notes: Trainer provides a recap of the Element asking questions to check trainee understanding and responding to questions from trainees, as required.

## Slide 179: Evaluate project
Performance Criteria for this Element are:
Assess project at specified stages, using agreed evaluation methods
Take account of agreed goals and priorities when carrying out a project evaluation
Involve project team members, appropriate colleagues and customers in the project evaluation
(Continued)
Notes: Trainer identifies for trainees the Performance Criteria for this Element, as listed on the slide.

## Slide 180: Evaluate project
Incorporate evaluation results into ongoing project management
Share information from project evaluation with appropriate colleagues and incorporate information into future planning
Report on planning
Notes: Trainer identifies for trainees the Performance Criteria for this Element, as listed on the slide.
Class Activity – Discussion
Trainer asks trainees questions about evaluating projects by asking questions such as:
How might a small project be evaluated?
What are the reasons for evaluating small projects?
Who may be involved in the evaluation process?
What topics might be evaluated?

## Slide 181: Assess project at specified stages
All projects should be assessed:
On an ongoing basis
At the end of the project
Notes: Trainer advises all projects should be assessed stating they should be assessed:
On an ongoing basis throughout the life of the project
At the end of the project when the project has been completed.

## Slide 182: Assess project at specified stages
Projects should be assessed by:
You – as the PM
Project team and relevant stakeholders
Notes: Trainer explains project should be assessed:
By you as the PM – on your own:
  You need to identify time for reviewing the project and comparing progress to the project plan.
  This may need to be done on a daily basis. It should be dome at least weekly.
  You need to develop your own perspective on the progress of the project.
By project team and relevant stakeholders:
  Contribute/make you aware of new factors you were previously unaware of
  Confirm your own impression of the progress of the project.
Class Activity – Guest Speaker
Trainer arranges for PM to attend and:
Identify activities in project evaluation
Describe those involved
Explain timing
Illustrate topics covered
Present sample project report.

## Slide 183: Assess project at specified stages
Opportunities for ongoing project assessment:
Daily briefing sessions
Daily debriefing sessions
Scheduled project team meetings
Specially convened project review and evaluation meetings
(Continued)
Notes: Trainer presents opportunities for ongoing assessment:
Daily briefing sessions with the project team undertaken at the start of each day.
  These sessions are ideal times for a group evaluation of the project and its progress.
  Certainly ‘project review/evaluation/assessment’ should be a standing topic at all staff meetings and briefings for those involved with the project.
Daily de-briefing sessions which is an ideal time to discuss progress or problems identified during the day/shift
Scheduled project team meetings
Specially convened project review and evaluation meetings to address specific topics/issues arising

## Slide 184: Assess project at specified stages
When complaints have been received
When significant problems occur
When key contractors indicate they cannot perform or complete as expected
When client requests changes to the agreed project management plan
Notes: Trainer continues presenting opportunities for ongoing assessment:
When complaints about the project are received
When significant problems with the project arise/are identified
When key providers/contractors indicate they are unable to perform their project obligations as agreed
When the client requests changes to the agreed requirements for the project.

## Slide 185: Assess project at specified stages
Evaluation options:
Surveys
Questionnaires
Workplace observation
Piloting
Capturing qualitative and quantitative data
Notes: Trainer reminds students of evaluation options:
Conducting surveys – talking to ‘relevant persons’ about the implementation and outcomes of the project.
Applying questionnaires to nominated people. These may be paper-based or online questions posed to solicit input and feedback about the project
Conducting workplace observation relating to project implementation and note-taking to provide a basis for later analysis
Engaging in pilots for aspects of the project. This features implementation of actual workplace trials of project elements to determine effectiveness, and reactions and responses from those who are impacted (such as clients, customers and staff) as well as funding bodies and delegating authorities
Capturing and analysing quantitative workplace data and qualitative data.

## Slide 186: Consider agreed goals and priorities
There must be a specific focus for project assessments and the following applies:
Should be ongoing and final assessment and review
Also known as ‘post mortem’
Assessment and review must reflect what was agreed in the planning process
Project management plan timelines for assessment and review must be complied with
Notes: Trainer advises there must be a specific focus for all project evaluations stating the following applies:
Assessments and reviews of the project must occur during the project
The project review at the end of the project is sometimes referred to as a post mortem
The end of project assessment and review (evaluation) phase for a project must reflect/implement the evaluation methods identified in the planning process
The timeline for assessment and review of the project as stated in the project management plan must be complied with.

## Slide 187: Consider agreed goals and priorities
Main reasons to assess/evaluate a project:
Confirm project status
Learn lessons
Review activities, issues and problems
Discharge ‘due diligence’
(Continued)
Notes: Trainer states the main reasons for assessing and reviewing projects are to:
Confirm project status. You need to verify the projected is truly completed/signed off, or whether there are still ongoing issues which still need to be resolved
Learn lessons which could be used for future projects so the next project does not repeat any mistakes of this project
Review activities, issues and problems relating to the project to identify what these were and (more importantly) why they emerged/occurred
Learn about how the venue and staff performed. Project reviews can provide useful insight into venue culture, general staff morale and individual staff performance
Discharge ‘due diligence’ requirements

## Slide 188: Consider agreed goals and priorities
Determine follow-up action required
Provide feedback to those involved
Identify any negatives of the project
Provide basis for reporting requirements
Formally complete the project management plan
Notes: Trainer continues stating the main reasons for assessing and reviewing projects are to:
Determine follow-up action which may need to be taken to put the finishing touches to a project and/or take remedial/corrective action to fix project-related problems
Provide useful, relevant and sought-after feedback to venue staff/teams who were involved in the project. Commonly those involved in a project also want to know how they performed
Identify actions taken by anyone in the project that functioned to impede the project such as, for example, instances where failure to complete a task caused the delay of another task, or sub-standard performance by a contractor
Provide detail and information to be used in formal reporting requirements for the project – reports can use information obtained as part of the review process
Formally complete/finalise the project management plan by fulfilling what is usually the last step/stage listed in the plan (‘Project evaluation/review’).

## Slide 189: Consider agreed goals and priorities
Topics for the review:
‘Anything’ related to the project
Funding levels and sources
Resources use and allocation
Timing issues
Personnel involved
(Continued)
Notes: Trainer presents topics to be covered in the review:
Anything related to the project – if ‘it’ was part of the project then it is potentially a subject of the assessment/evaluation
Funding levels and sources:
  Were sufficient funds allocated/provided to enable achievement of project deliverables?
  Were the best funding sources accessed for the project?
Resource use and allocation:
  Were appropriate, sufficient, compliant resources used and/or made available?
  Were the resources made available actually suitable for the project?
Timing issues:
  Was there sufficient lead time to enable appropriate planning?
  Did staff used in the project have enough time to do their project-related work as well as other ‘normal’ venue duties?
Personnel involved in the project:
  Did you use ‘the right staff’ from within the business, and from outside agencies/businesses?
  Did you have sufficient staff involved?

## Slide 190: Consider agreed goals and priorities
Role of stakeholders
Problems encountered
Evaluation against the project management plan
Budget
Lessons learned
Notes: Trainer continues presenting topics to be covered in the review:
Role of stakeholders in the project:
  Did they actually perform within the project as they promised?
  What advantages and disadvantages were there in having these stakeholders involved?
  Who would you want or not want next time, and why?
Problems encountered:
  What unforeseen issues and problems occurred during the project?
  How were they addressed and could they have been addressed more effectively?
  How can these situations be avoided nest time?
Trainer continues presenting topics to be covered in the review:
Evaluation of the project against the project management plan – all elements of the project plan should be subject to review (see Class Activity, below)
Budget – there is always a need to consider ‘budget’ in any project review:
  Were there cost over-runs?
  If so, to what extent and why?
  Could the cost blow-outs have been predicted? Avoided?
  Did the project make the moist effective and efficient use of the funds (and other resources) provided for it?
Lessons learned – see later slides
Class Activity – Question and Discussion
Trainer asks students to identify elements of the project management plan which should be evaluated.
Possible answers:
How effective was the plan? Was the project plan sufficiently detailed, instructive and focussed?
Did the project management plan provide sufficient guidance for the project?
To what extent were the deliverables, objectives, outcomes and other items in the project plan actually achieved?
If there was a discrepancy between ‘actual’ and ‘expected’ outcomes, are these acceptable?
Why did they occur?
Did those nominated in the project plan discharge their allocated responsibilities?
Were designated timelines adhered to? If not, why not?
Were all compliance requirements achieved?
How effective, with the benefit of hindsight, was the risk management for the project?
Were all actual risks identified and effectively addressed/managed?

## Slide 191: Consider agreed goals and priorities
To conduct effective project assessment:
Review against criteria
Include others in the process
Schedule review meetings
Forward documents to stakeholders for pre-reading prior to scheduled meetings
(Continued)
Notes: Trainer identifies the following points will help undertake an effective project assessment:
Review the project against the criteria, milestones, KPI and other relevant criteria you said you were going to review it against
Be inclusive and make sure all necessary stakeholders are included in the review process or have an opportunity to make input or comment
Schedule the review meetings and give those who are to attend plenty of notice about the time, date, location and expected duration of meetings.
  It is best to schedule these meetings soon after the project has been completed so things are still fresh in people’s minds
Forward any relevant documents to these people so they can pre-read them and attend the meetings informed about what is to be discussed

## Slide 192: Consider agreed goals and priorities
Establish standard protocols to facilitate the process
Make sure everyone knows the process is not a witch hunt
Take the review and assessment seriously
Circulate the findings to stakeholders
Notes: Trainer continues identifying points to help undertake an effective project assessment:
Establish standard documents and filing protocols to facilitate the review and all subsequent reviews.
  Try to avoid a situation where documents need to be developed anew every time a project review occurs
Make sure all internal staff involved in the review are aware the process is not a witch hunt. The review must be characterised by honest and comprehensive input from participants so it is important they realise the focus is on gathering information rather than allocating blame
Take the review of the project as seriously as you did the planning and execution of the project. The review is an integral part of the project, not just an after-thought
Circulate the ‘findings’ of the review to stakeholders as identified by management/the Steering Committee.

## Slide 193: Involve project team members
Involvement in the review process for a project:
Some venues will be ‘all inclusive’
Some venues will be more selective about who can participate
Type and scope of the project will be a primary indicator
Management/Steering Committee may direct who is to be involved
Notes: Trainer discusses involvement of others in the review process stating:
Some venues will be ‘inclusive’ and allow ‘all stakeholders’ to participate
Some venues will restrict external stakeholders who are allowed to participate in the process
Type and scope of the project will be a big factor in identifying who should be involved
Management/the Steering Committee may advice who is to be involved

## Slide 194: Involve project team members
Those who may/could be involved in the evaluation:
Management/Steering Committee
Project team members
Representatives from external bodies
Staff who helped implement the project
Staff impacted by the project
Internal support staff
Customers/guests
Notes: Trainer presents options for involvement in the project evaluation:
Management
Steering Committee
Project team members where a team (or similar) was developed to manage and/or discharge the requirements of the project
Representatives from external professional organisations/bodies – accountants, legal advisers, government agencies
Staff/team members involved in implementing/executing the project
Staff/team members on whom the project impacted but who were not involved in its execution
Internal venue ‘support staff’ such as bookkeepers, store personnel, anyone whose work was associated with assisting in the organisation/execution of the project
Customers and guests on whom the execution of the project impacted and on whom any ‘finished product’ (new facilities, revised menus, refurbished rooms) impacts.

## Slide 195: Involve project team members
Tips to enhance the review process:
Minimise time people are expected to commit to the process
Time meetings at times to suit those attending
Encourage participation
Reward those who attend
(Continued)
Notes: Trainer advises the following are useful tips which have proved effective in the review process:
Try to minimise the time people are expected to commit to the review process – do not drag it out
Time the meeting/s at suitable times to optimise the chance of people attending.
  Staff should be paid to attend/required to attend during work hours
Actively encourage participation – speak to those you want to attend and encourage them to turn up and take part.
  Urge them to actively participate.
Reward people for attending by, for example:
  Verbally thanking them for their time and input
  Providing refreshments or a meal as part of the review/assessment meeting
  Sending participants a ‘letter of thanks’

## Slide 196: Involve project team members
Encourage honest input to the process
Ask questions to motivate feedback
Structure the session:
Introduction
Body
Q and A
Conclusion
Notes: Trainer continues advising the following are useful tips which have proved effective in the review process:
Encourage people to provide honest input (in their eyes/from their perspective) – stress the review process is not intended to rubber-stamp what has occurred
Ask questions to motivate them to give feedback/make comment – do not rely on participants to ‘give’ information
Structure the review session – take time to plan it so it has:
  An Introduction – explaining what the session will cover
  A Main Body – this is the structured set of questions to be asked to solicit feedback. You will need to have identified the areas you want feedback on, and phrase the questions so they are not ‘loaded’ or biased
  A ‘Question and Answer’ session to enable input on issues not addressed by the structured questions
  A Conclusion – which should include thanks to those who attended; an indication of future projects; explanation of action to be taken on the basis of feedback received.

## Slide 197: Incorporate results into ongoing project management
Outcomes or findings of project evaluation need to be factored into ongoing and future project management.
The evaluation must address:
Processes
and
Products
Notes: Trainer explains outcomes/findings of project evaluation need to be factored in to ongoing project management and future project management highlighting the evaluation process must consider:
Processes – that is, the actions taken to achieve the outcomes/project deliverables
Products – the end result of action taken: the outcomes/project deliverables as they exist at the point the evaluation is being undertaken.
The findings of the evaluation against these two criteria are what must be factored in to ongoing project management.
Class Activity – Question and Discussion
Trainer asks students to identify examples of ‘processes’ and ‘products’ for projects.

## Slide 198: Incorporate results into ongoing project management
Action to take to factor in evaluation results must:
Reflect actual evidence
Address processes and products
Comply with limitations imposed on the project
Notes: Trainer states the action to take to factor in evaluation results must:
Reflect actual evidence gathered for/as part of the evaluation process as opposed to reflecting unsubstantiated beliefs and assumptions
Address both ‘processes’ and ‘products’
Fall within the parameters, obligations and restrictions for the project.

## Slide 199: Incorporate results into ongoing project management
Incorporating results may mean:
Very rare need to make major changes to initial project management plan
Need to source extra resources
Need to make adjustments
(Continued)
Notes: Trainer presents practical considerations in terms of incorporating project results into ongoing project management:
Rarely need to make significant/major changes to your project management plan.
  Most changes which are identified as being necessary on the basis of ongoing evaluation throughout the life of a project are relatively small. They are more a ‘fine tuning’ of the plan rather than a re-writing of the plan
May need to source additional resources to enable completion of the project as planned
May need to adjust to various elements – see Class Activity (below).
Class Activity – Question and Discussion
Trainers asks students to identify aspects of the project which may need to be adjusted on the basis of ongoing review.
Possible answers:
Staffing – such as the hours for staff, the mix of workers and the number of personnel
Completion time for nominated tasks, stages and the final product
Alter other aspects of the plan such as:
Resources
Responsibilities
Providers
KPIs
Elements of identified Stages
Milestones
Quality criteria.

## Slide 200: Incorporate results into ongoing project management
Need to communicate and share with stakeholders
Need to gain approval for changes which are necessary
Need to distribute revised changes or revised project management plan to stakeholders
Notes: Trainer continues presenting practical considerations in terms of incorporating project results into ongoing project management:
Should communicate to stakeholders:
  The findings of the progressive evaluations – advising them of all relevant points, the positive and the negative
  Explaining reasons for required changes and explaining the causal factors
Will need to seek approval for changes you intend making for the agreed/original project management plan
Must distribute the revised project management plan to those who received a copy of the original project plan. There may be a need to hold a meeting to present/explain the revised plan.

## Slide 201: Share and incorporate findings into future planning
‘Lessons learned’ must be evidence-based.
Documenting lessons learned involves:
Writing them down
Attaching supporting evidence
Communicating the lessons
Filing relevant documents
Notes: Trainer states it is not sufficient to simply ‘discuss’ the project when reviewing it explaining a primary objective of the review should be the documentation and retention of information which can be beneficially used by the venue when future projects are undertaken highlighting:
Any lessons learned must be based on ‘evidence’ as opposed to subjective impressions.
Documenting lessons learned involves:
  Writing down the lessons learned describing the situation/s that gave rise to the lesson, and what the exact nature of the lesson is (that is, how subsequent projects should take into account the lessons learned)
  Attaching supporting/accompanying documentation to the lesson such as (as appropriate) written feedback from stakeholders, sections of legislation, copies of quotes, invoices, product samples or letters of complaint
  Including basic data – name of the project, details of project team/management team, date/s, and base project documents used in the project (such as the project management plan)
  Communicating the lessons learned – see later slides
  Filing the documents and data. Filing will/should occur in a physical, paper-based format and electronic format.
    Attention must be paid to ensuring ‘relevant others’ know where this information and/or documents are physically located so they can access it when required.
    Standard filing protocols should apply to ensure:
      Security
      Protect confidentiality
      Track/record use of the documents.
Commonly, lessons learned are not ‘generally’ distributed – that is, they are not usually communicated to external stakeholders or ‘the public’.
Class Activity – Guest Speaker
Trainer arranges for experienced PM to attend and:
Discuss evaluation and assessment process for a project
Give examples of lessons learned
Identify how these lessons were learned
Describe how these lessons learned were integrated into future project management.

## Slide 202: Share and incorporate findings into future planning
To optimise chance of lessons being learned for future projects:
Circulate findings and lessons learned amongst other PMs
Integrate findings into venue training
Revise policies and SOPs as required to incorporate lessons
Hold special staff meetings to explain
Provide mandatory SOPs for PM which require reference to previous projects
Notes: Trainer states to help optimise inclusion of lessons learned from past projects into future projects the following can be applied:
Circulate lessons learned to other PMs within the venue and meet to discuss them
Integrate lessons learned into venue training for project managers
Revise venue policies and procedures to include the lessons learned, ensuring version control protocols are implemented to maintain currency of documents
Hold special staff-management meetings to discuss the lessons learned
Provide SOP for project managers which makes it mandatory for them to:
  Talk to previous PMs before they start planning a project
  Read/review evaluations (‘lessons learned’) from previous projects.

## Slide 203: Share and incorporate findings into future planning
Ways to share and communicate lessons learned:
Verbal report to management
Verbal report to stakeholders
Formal presentation
Evaluation sheet
Formal report
Meet with key persons
Notes:   Trainer presents ways to share project information/lessons:
  Make a verbal report to management. This may be all that is required in many cases for a small project
  Make a verbal report to nominated stakeholders – internal and/or external
  Do a formal presentation on the findings which will entail a need to:
    Verbally present the final evaluation
    Explain aspects of it
    Defend decisions made
    Justify expenditure
    Confirm or clarify points arising
    Provide supporting/evidentiary documentation
  Complete and return an Evaluation Sheet as and if required by a client, funding body or delegating authority
  Circulate a formal report on the project – see next section
  Meet with key internal figures to discuss the findings. These would include:
    Managers and supervisors
    Other people with project management responsibilities
    Trainers and training staff so they integrate findings into in-house trainers
    Those with responsibility for preparing and updating venue policies and procedures so findings can be formalized into internal SOPs.

## Slide 204: Report on project
Contents of Project Report would include:
Name/title of project
Name of venue
Name of project
Name of those who prepared report
Date
Type of report
(Continued)
Notes: Trainer suggests all projects will require some form of report when the project has been finalised identifying the following points are commonly addressed in relation to contents of Project Reports:
Name/title of the Report – ‘Review and upgrade of in-house training’
Name of the venue
Name of the Project
Name of the person/s who prepared the Report
The date/period to which the Report applies
Identification of nature of the Report – for example, ‘First Interim Report’, ‘Final Report’

## Slide 205: Report on project
Executive Summary
Relevant KPIs, milestones and stages
‘Actual’ progress matched against ‘projected’ progress
Budget
Personal observations as PM
Notes: Trainer continues identifying contents of Project Report:
Executive Summary – a single page synthesising the content of the report
KPIs, milestones and stages the project management plan identified as being applicable in relation to this Report
Actual progress matched against the stated criteria identifying reasons for above and/or below expected outcomes
Budget
Your observations as PM. Your Project Notebook should be used to help write this section of the Report. You may raise topics such as:
  Unexpected delays
  Problems with suppliers/contractors and/or venue-based project staff
  Instances of unacceptable work which has had to be re-done
  Unexpected impacts of the project on customers or normal venue operation
  Emerging safety issues and hazards
  Suggestions/recommendations for action to address identified issues, time lags, sub-standard quality issues and others issues raised in the Report.
Class Activity – Handout
Trainer distributes and discusses an example of a Project Report.

## Slide 206: Report on project
All project reports are ‘commercial-in-confidence’.
Ways to distribute the reports:
By hand
Electronically
Intranet
Standard postal system
Courier
Notes: Trainer remarks all project reports must be treated as commercial-in-confidence indicating common ways to forward reports are:
By hand – distributing appropriately-bound hard copies.
  Distributing by hand also allows you to talk to the report when you hand it over
Electronically – via email.
  Take care to double-check the correct email address is being used. It is not standard practice to send reports by facsimile
Using the intranet
Using the postal system or couriers to deliver hard copies to external stakeholders.

## Slide 207: Summary – Element 3
When evaluating project:
Ensure you allocate time for scheduled assessments
Involve relevant internal and external stakeholders
Schedule meetings for formal evaluations and assessments
Address ‘process’ and ‘product’ issues
(Continued)
Notes: Trainer provides a recap of the Element asking questions to check trainee understanding and responding to questions from trainees, as required.

## Slide 208: Summary – Element 3
Assess actual project performance against planned performance
Use the project management plan as the basis for evaluation, assessment and review
Adjust the project plan on the basis of assessment/review findings
Incorporate evaluation results into ongoing project management for the project being assessed
(Continued)
Notes: Trainer provides a recap of the Element asking questions to check trainee understanding and responding to questions from trainees, as required.

## Slide 209: Summary – Element 3
Obtain necessary authorisations for project plan revisions and amendments
Circulate copies of the revised project plan
Share the findings of the evaluation
Factor in lessons learned into future project management activities
Prepare and distribute a report on the project
Notes: Trainer provides a recap of the Element asking questions to check trainee understanding and responding to questions from trainees, as required.
Trainer thanks trainees for their attention and encourages them to apply course content as required in their workplace activities.